## 00-Cover
Sheet: 00-Cover
Slide 1 of PPTX template. First sheet the reader sees.
Block 1 — Title
Project Plan Future — Planner MVP
Block 2 — Subtitle
A complete, enterprise-grade project kick-off playbook — scope, timeline, resourcing, governance, risk & AI differentiator.
Block 3 — Metadata
Field | Value
Document | Project Plan
Project | Future — Planner MVP + Core Backend + Core Frontend + Core AI Agent
Version | 1.0
Date | 22 Apr 2026
Owner | Canh Ta (PM), Nguyen Hương Ly
Classification | Internal — SETA Confidential
Block 4 — Approvers
Name | Role | Signature | Date
Hung Vu | CEO — Project Owner and Sponsor
Thu Mai | CTO — Technical Sponsor and Platform Architecture Authority
Hoang Nguyen | PMO Representative
Block 5 — Footer
Enterprise Project Plan · Confidential · Prepared by SETA PMO

## 00-TOC
Sheet: 00-TOC
Slide 2 of PPTX template. Table of Contents with hyperlinks to each sheet.
Block 1 — Table of Contents
# | Section | Sheet | Covers
01 | Project Overview | 01-Overview | Problem · Solution · SMART Objectives · Info
02 | Project Contract | 02-Contract | Contract · Milestones · Acceptance
03 | Estimation & Scope | 03-Scope | WBS · In/Out · Change Request
04 | Project Timeline | 04-Timeline | Master plan · Milestone · Sprint · Holiday calendar
05 | Project Approach | 05-Approach | Org · SDLC · QA · CI/CD · AI differentiator · Definition of Success
06 | Resource Management | 06-Resources | Allocation · RACI
07 | Dependencies, Constraints, Assumptions | 07-DCA | Dependencies · Constraints · Assumptions
08 | Risk & Issue Management | 08-Risks-Issues | Register · Heat map · Issues · Process
09 | Executive Support | 09-ExecSupport | Budget · Decision SLA · Kill criteria
T1 | Track — Planner | Track-Planner | User-facing Planner module track
T2 | Track — Core Backend | Track-CoreBackend | Foundational BE slice
T3 | Track — Core Frontend | Track-CoreFrontend | Foundational FE slice
T4 | Track — Core AI Agent | Track-CoreAIAgent | Foundational AI Agent slice (Phase 1 + 2)
Block 2 — How to navigate
• Cell hyperlinks: each row's "Sheet" column is a hyperlink to the named sheet (set via HYPERLINK("#'<sheetname>'!A1", "<sheetname>")).
• Tables use filter headers and banded rows.
• Cell fills carry status colour per 04-Timeline Block 4 Status Legend.

## 01-Overview
Sheet: 01-Overview
PPTX Slides 3-5. Info + Problem/Solution + Key Components + SMART Objectives.
Block 1 — Information (field/value grid)
Field | Value
Project Name | Future — Planner MVP (with foundational Core Backend, Core Frontend, Core AI Agent slices)
Business Model (BMM) | Internal · Cost-saving
Duration | 22 Apr 2026 → full-coverage rollout (TBD)
Project Type | Internal build · Non-billable
Methodology | Agile Scrum · 2-week sprints
Stakeholders | Hung Vu (CEO, Sponsor) · Thu Mai (CTO, Technical Sponsor) · Hoang Nguyen (PMO) · Pilot team (TBD W6)
Budget | Team time + 1× Claude Max x20 shared subscription + ~$200 AI API cap. No dollar project budget. Infrastructure + MS 365 licences covered under existing organisational accounts.
Version | 1.0 — first published 22 Apr 2026
Block 2 — Problem & Solution
Current pain point
SETA's ~400 staff make commitments constantly — in standups, ceremonies, client calls, account reviews, leadership syncs, kickoffs — and those commitments live in Teams chats, personal notes, and people's heads. This produces five operational costs:
• The chase-up tax. Managers spend a meaningful share of their week pinging team members on Teams about earlier commitments. It does not appear in timesheets but consumes real time and creates friction.
• No authoritative record. When a manager asks, "What did we agree on last Thursday?" there is no single place to look.
• Completion without evidence. "Done" means the owner said so — insufficient for high-stakes commitments.
• Portfolio blindness. Leadership, line managers, and PMO cannot see in real time whether their area is healthy. Status is compiled manually on weekly cycles, stale by the time it is read.
• Strategic commitments evaporate. Commitments made in leadership meetings carry the highest stakes and are the most likely to be forgotten, because the people making them are the busiest.
Solution
Future's Planner module captures commitments made in Microsoft Teams meetings, tracks them to completion with evidence, synchronises bidirectionally with Microsoft Planner, and surfaces aggregated health views at every level of SETA's org chart. The Agent module (Core AI Agent + transcript-driven extraction) reduces the chase-up tax through AI-with-human-oversight. The conversational AI interface gives every role a natural-language way to query their action and meeting data.
This MVP also proves out four foundational Future modules — Core Backend, Core Frontend, Core AI Agent, and (contingent on Data Engineer onboarding) Core Data Platform — that every subsequent Future module will reuse.
Block 3 — Key Components
# | Component | Role in MVP
1 | Planner (user-facing) | Action tracking, evidence capture, Meetings page, HITL review queue, aggregated views, executive digest, Microsoft Planner bidirectional sync. Built on top of Core BE + FE.
2 | Core Backend | Identity (Entra ID SSO), org-chart permissions engine (NFR-04), audit logging, RLS, MS 365 integration (Teams transcript webhook, Planner API, Entra directory read), outbound email gateway.
3 | Core Frontend | Shared UI component library (@future/ui), design system per DESIGN.md, layout + navigation primitives (@future/app-layout), multi-zone pattern for 11 zones + web-shell.
4 | Core AI Agent (two phases) | Phase 1 (W1–W4): LLM client, prompt management, confidence scoring, HITL routing engine, bounded tool/MCP registry. Phase 2 (W5–W8): Fine-tuning, security hardening (prompt-injection defence, permission enforcement at AI boundary, adversarial testing), free-form conversational queries beyond Phase 1 registry.
Out of build but feeds into: Core Data Platform (Glue → Iceberg → Athena) runs on Core Data Platform timeline if DE onboarded by W1; otherwise deferred, aggregated views/digest run on direct operational DB for the MVP.
Block 4 — SMART Objectives
# | Objective | Metric | Target | Timeline | Owner
G1 | Reduce manager chase-up effort | Pilot managers' time-diary minutes spent chasing actions | Meaningful reduction W1-baseline → W4-pilot; fewer than 1/3 ICs report nudges unnecessary | Pilot W4 | PM
G2 | Establish authoritative record of commitments | Pilot Week-4 interview: "did you also write it down elsewhere?" | < 1/3 of pilot users still keep side-records | Pilot W4 | BA
G3 | Give every hierarchy level a useful area overview | Leadership interview (5 leaders × 3 questions: saw it? acted on it? miss it if gone?) | ≥ 2 of 5 answer yes concretely to all three | Pilot W4 | PM
G4 | Catch commitments previously lost | BA manually extracts actions from ~12-20 sampled meetings; compared to Agent recall | Recall ≥70%; reviewer acceptance ≥70% | Pilot W4 | BA + AI Eng
G5 | Build foundational modules that extend cleanly | CTO architectural-review pass/fail on interface fitness | Pass (no rework needed for future modules) | W8 gate | CTO
G6 | Prove the AI-with-human-oversight pattern | HITL acceptance rate · review latency · reviewer feedback | Acceptance ≥70%, median latency ≤24h, reusable pattern | Pilot W4 | AI Eng
G7 | Establish natural-language interaction as first-class | ~30 sampled conversational queries — first-attempt correctness | ≥80% first-attempt correctness; no permission-leak incidents; ≥50% of interviewed pilot users have tried and find useful | Pilot W4 | AI Eng

## 02-Contract
Sheet: 02-Contract
PPTX Slides 6-7. Internal Charter (contract-equivalent for internal project) + Milestones & Deliverables + Legal & Compliance checklist.
Block 1 — Internal Charter Fields
Field | Detail
Charter ID | FUTURE-PLANNER-MVP-2026-01
Sign Date | 22 Apr 2026
Parties | SETA (internal project) — no external client
Sponsor | Hung Vu (CEO) — Project Owner
Technical Sponsor | Thu Mai (CTO) — Platform Architecture Authority
PMO Representative | Hoang Nguyen
Payment Model | Internal — no billable milestones. "Payment %" template column is repurposed to Acceptance Weight (unitless) to reflect gate strictness.
SLA | Internal — formal uptime SLA is explicitly out of scope for this MVP. Pilot-phase operational response times captured in 05-Approach Block 3 Escalation SLA.
Governance | Steering Committee monthly (PM + Sponsor + CTO + PMO) · PM weekly sync with sponsor · Sprint Review biweekly · Retro biweekly. Detail on 05-Approach Block 4.
Termination / exit | "Termination" in the internal charter = Pilot-to-Wave gate decision at W12. Kill criteria on 09-ExecSupport Block 3.
Block 2 — Milestones & Deliverables
Status legend colour applies per 04-Timeline Block 4.
ID | Milestone | Planned | Actual | Owner | Key Deliverable | Acceptance Criterion | Acceptance Weight | Status
M00 | Kickoff | Wed 22 Apr 2026 · W1 |  | PM | Project Plan v1.0 signed · track leads named · Kickoff Open Questions closed by EOW | Sponsor approval recorded on this sheet | 5% | Planned
M01 | Core Foundations ready | Tue 05 May 2026 · W2 end |  | Tech Lead | Identity + permissions + audit + RLS + outbox operational; design system tokens locked; AI Phase 1 deps installed; Agent runtime gateway stub running | Smoke tests green across API + each zone; internal demo passes | 10% | Planned
M02 | Core AI Agent Phase 1 complete | Tue 19 May 2026 · W4 end |  | AI Engineer | LLM client + prompt store + confidence scoring + HITL routing + bounded tool registry + Langfuse telemetry | Phase 1 exit-criteria suite green (on Track-CoreAIAgent Block 5); read-only sub-agent responds to smoke queries within SLA | 15% | Planned
M03 | First Working Version (internally demoable) | Tue 19 May 2026 · W4 end |  | PM | Planner action CRUD, Personal Hub, Meetings page shell, HITL review queue (wired to Agent Phase 1), minimal aggregated view, basic admin console | Internal demo to sponsor + CTO passes; no critical bugs; ≥70% coverage across changed modules | 15% | Planned
M04 | MVP Pilot-ready | Tue 16 Jun 2026 · W8 end |  | PM | Complete Planner feature set · executive digest · MS Planner bidirectional sync · conversational AI interface · pilot team nominated · measurement instruments ready | Pre-pilot gate criteria on 05-Approach Block 12 Definition of Success all green; sponsor go/no-go | 25% | Planned
M05 | Core AI Agent Phase 2 complete | Tue 16 Jun 2026 · W8 end |  | AI Engineer | Prompt tuning · prompt-injection defence · permission enforcement at AI boundary · free-form query router · adversarial security test suite passing | Penetration-style test by PM/BA returns zero permission-leak incidents; conversational interface first-attempt correctness ≥80% on baseline set | 10% | Planned
M06 | Pilot-to-Wave gate | Tue 14 Jul 2026 · W12 end |  | Steering Committee | Pilot 4-week report with outcome measures; Kill-criteria evaluation; Go / pause-and-tune / pivot decision recorded | Committee decision recorded in this sheet; kill-criteria thresholds evaluated on 09-ExecSupport | 10% | Planned
M07 | Wave 1 rollout complete | TBD (post W12 gate) |  | IT + PMO | First rollout wave (~2 weeks); wave health report | No critical blocking issues; adoption metric maintained | 5% | Planned
M08 | Full-coverage rollout complete | TBD |  | IT + PMO | All target users provisioned; legacy side-channel parking | Active-user count reached target; side-channel tracking stopped | 3% | Planned
M09 | Post-rollout review | TBD |  | PM + Steering Committee | 4-week stable-operation report; next module scoped | Committee sign-off on Future roadmap continuation | 2% | Planned
Total acceptance weight: 100%.
Block 3 — Legal & Compliance Checklist
Template-native checklist from PPTX Slide 6, adapted for internal project.
# | Item | Status | Owner | Note
1 | NDA signed | N/A | Legal | Internal project — all participants under existing SETA employment NDAs
2 | Data protection & privacy clause (GDPR / local law) | Pending W2 | PM + Legal | Apply SETA internal Data Protection Policy; align with VN Decree 13/2023 on Personal Data Protection; no external data processors beyond OpenAI (covered under Block 4 vendor disclosure)
3 | IP ownership & license scope | Confirmed | CTO | SETA-owned across all codebases; no third-party IP licensing required for this MVP; OSS dependencies tracked in SBOM (auto-generated by CI per 05-Approach Block 10)
4 | Vendor data-processing disclosure | Pending W1 | PM | Approval of this charter acknowledges action content and transcript excerpts are transmitted to OpenAI for Agent extraction under SETA vendor and data policies
5 | Audit-log retention policy | Pending W4 | CTO | Indefinite retention per regulatory baseline; no audio stored; archival/pruning strategy locked before pilot
Block 4 — Regulatory Context
• Authentication: Microsoft 365 SSO via Entra ID exclusively; no local accounts. Aligns with SETA identity standards.
• Data captured: Names, work email, team membership, reporting structure (from Entra ID); Teams-produced transcript text content. No audio stored. No biometric data.
• Meeting consent: Handled natively in Microsoft Teams; platform inherits the Teams posture. User-level opt-outs per BRD REQ-12 add an additional privacy layer.
• Data residency: All infrastructure in AWS ap-southeast-1 (Singapore). No region leakage; cross-region access is blocked at infrastructure level.
• AI-originated actions: Distinguishable from human-originated actions in the audit log (per 05-Approach Block 6 DoR/DoD, audit event schema).
• Cross-hierarchy raw access: Every Admin-initiated cross-hierarchy read is logged with a stated reason. Enforced by Core Backend permissions engine.

## 03-Scope
Sheet: 03-Scope
PPTX Slides 8-10. WBS-Master (feature-level rollup) + In/Out of Scope + Change Request process + CR log.
Decomposition convention
Tracks split horizontal vs vertical:
• Horizontal tracks — Core Backend, Core Frontend, Core AI Agent. Monorepo scaffolding, shared auth, common components/utilities, routing, caching, base observability, permission primitives, LLM plumbing. No module-specific code. Built once; reused by every Future module.
• Vertical track — Planner. Integrates the three Core horizontal slices into a user-facing product. Every Planner feature has its own BE handlers, FE UI, and (where relevant) Agent-integration sub-work.
The Planner WBS therefore contains Planner-BE rows, Planner-FE rows, and Planner-Agent-integration rows. The Core tracks contain only horizontal primitives.
Block 1 — WBS-Master (feature-level rollup)
Effort in MD (man-days). Confidence: H = well-understood, M = some novelty, L = material unknowns. Layer: BE / FE / AI / BE+FE / BE+AI / FE+AI indicates which technical layer(s) the feature spans. Sprint column targets S1–S4 (W1–W8).
Ownership convention: Owner = FS#1 or Owner = FS#2 identifies a single full-stack dev who owns that feature end-to-end — BE + FE + any integration layer. There is no BE-vs-FE split between the two FS devs. Per-feature ownership is provisional in the Owner column and finalised at Kickoff. Owner = AI Eng identifies the AI Engineer as end-to-end owner (including the BE hooks needed to integrate). Non-builder rows (PM / PO / SM / BA / QA) carry the respective role name.
Core Backend (horizontal)
ID | Module | Function | Feature | Layer | Effort Low | Effort High | Confidence | Owner | Sprint | Acceptance
W-B01 | Monorepo | Scaffolding | Turborepo · bun workspaces · shared tsconfig / eslint / prettier / lefthook · workspace package template | BE | 2 | 4 | H | FS#2 | S1 | turbo build green from clean clone; new workspace via turbo gen workspace; pre-commit runs lint + format + type-check
W-B02 | Monorepo | DDD module template | Hexagonal + DDD generator (domain / application / infrastructure / interface-trpc / module.ts) per project convention | BE | 2 | 3 | H | FS#2 | S1 | nest g resource produces compliant layout; module exports QueryFacade only; lint rule blocks cross-module domain/infra imports
W-B03 | Auth | Entra ID SSO primitive | OAuth flow · session cookie · refresh · logout · tenant metadata | BE | 3 | 5 | H | FS#2 | S1 | Sign-in round-trip against test tenant; session cookie httpOnly + SameSite; logout revokes locally and at IdP
W-B04 | Auth | Magic link primitive | Token mint · deliver via email gateway · validate · single-use | BE | 2 | 3 | H | FS#2 | S1 | End-to-end magic-link flow tested; token TTL enforced; replay rejected
W-B05 | Permissions | Org-chart permissions engine | rolegrant · rolepermission · delegation · effective-permission resolver · canDo() API | BE | 5 | 8 | M | FS#2 | S1–S2 | Role resolution respects direct + delegated + cross-hierarchy cases; unit tests cover every matrix cell
W-B06 | Permissions | tRPC permission middleware | Guard annotations · P2 visibility helpers · cross-hierarchy raw-access audit hook | BE | 2 | 4 | M | FS#2 | S2 | Middleware denies with structured error; denial logged; P2 scope enforced in list endpoints
W-B07 | Audit | Audit log primitive | Audit event schema · KernelAuditFacade · insert-only guarantees | BE | 2 | 3 | H | FS#2 | S1 | Every AI op, approval, export, admin action, opt-out, scope change, cross-hierarchy read logs an event; query by actor/subject/operation
W-B08 | Infra | RLS + tenant middleware | app.tenant_id set per request · pool-client-per-request · Promise.all-on-DB lint rule | BE | 2 | 3 | H | FS#2 | S1 | Cross-tenant query denied at DB layer; lint rule blocks Promise.all on DB queries in handlers
W-B09 | Events | Outbox + polling relay | outbox_event schema · relay worker · at-least-once delivery · dead-letter policy | BE | 3 | 5 | H | FS#2 | S1 | Events published transactionally with owning write; relay delivers to pg-boss at-least-once; DLQ visible
W-B10 | Jobs | pg-boss harness | Worker scaffolding · retry / backoff · scheduled-job helpers · graceful shutdown | BE | 2 | 3 | H | FS#2 | S1 | Worker process runs jobs; retries on transient error; scheduler survives leader change
W-B11 | Rate Limiting | Rate limiter primitive | Per-user + per-tenant limiter · storage in Redis or Postgres · bypass for admin | BE | 2 | 3 | H | FS#2 | S2 | 429 returned at threshold; counters reset per window; admin override recorded
W-B12 | Kill switch | Kill-switch primitive | Per-capability flags · admin toggle · cached with invalidation · surfaced in 05-Approach Block 11 AI differentiator surface | BE | 2 | 3 | M | FS#2 | S2 | Toggle disables route atomically; audit event recorded; deterministic paths keep operating
W-B13 | Email | Outbound email gateway | SES (prod) + SMTP (dev) transport · template registry · per-tenant from-address · unsubscribe token | BE | 3 | 5 | H | FS#2 | S1 | Template-driven emails send; bounce captured back to user; rate limits respected
W-B14 | MS Graph | Graph adapter scaffolding | Graph client wrapper · retry / backoff · rate-limit-aware batching · delta-query helper · subscription-renewal scheduler | BE | 4 | 6 | M | FS#2 | S2 | Client handles 429 with backoff; subscription-renewal job runs ahead of expiry; delta queries batch
W-B15 | Observability | OTel + Langfuse bridge · CloudWatch logs | OTel instrumentation · Langfuse span export · structured logging · request-id propagation | BE | 2 | 3 | H | FS#2 | S1 | Every tRPC call appears as span; trace IDs propagate across worker boundaries
W-B16 | Commons | Shared BE utilities | Error types · serializers · ID generators · clock abstraction · zod schema helpers · request-scoped context | BE | 2 | 3 | H | FS#2 | S1 | Utilities unit-tested; clock injected for time-sensitive handlers; IDs deterministic in tests
W-B17 | Admin module | Scaffolding | Tenant settings · system settings · module toggles · feature flags · IdP config storage · email transport config · AI config (per-capability enable / kill switches surfaced to Admin UI) | BE | 3 | 5 | M | FS#2 | S1–S2 | Admin tRPC routes exposed; settings read/write round-trip; every change audited
W-B18 | @future/mail | Mail package boundary | Transport abstraction (SES / SMTP) · template registry · template rendering (MJML or React Email) · unsubscribe token · bounce + complaint handler · suppression list | BE | 3 | 5 | H | FS#2 | S1 | Templates render cleanly in Gmail / Outlook / Apple Mail; bounce event suppresses future sends; unsubscribe honoured
W-B19 | @future/storage | Storage package | S3 presigned-URL wrapper (upload + download) · mime-type guard · max-size guard · per-tenant prefix | BE | 2 | 3 | H | FS#2 | S1 | Upload + download round-trip; guards enforced; cross-tenant path access blocked by prefix
W-B20 | @future/db | DB package | Drizzle migration runner · schema helpers · connection-pool wrapper · transaction helpers · repository base class | BE | 2 | 3 | H | FS#2 | S1 | Migrations run deterministically; repository base supports tenant-scoped queries by default
W-B21 | @future/event-contracts | Events package | Plain-TypeScript event shapes across modules · zero NestJS deps · versioned contract per event | BE | 1 | 2 | H | FS#2 | S1 | Packages consuming events don't pull Nest runtime; version bumps are explicit CRs
Core Frontend (horizontal)
ID | Module | Function | Feature | Layer | Effort Low | Effort High | Confidence | Owner | Sprint | Acceptance
W-F01 | Monorepo | Multi-zone setup | Next.js multi-zone (11 zones + shell) · routing conventions · zone proxy · shared Next config | FE | 3 | 5 | H | FS#1 | S1 | Every zone boots independently; cross-zone hard-link discipline via lint; shell owns SSO + magic link
W-F02 | Design System | Tokens + Tailwind | Design tokens (color · type · spacing · radii · motion) · Tailwind v4 config · CSS variables · dark (default) + light | FE | 2 | 4 | H | FS#1 | S1 | Tokens drive every component; lint flags hardcoded colors; theme tokens validated
W-F03 | UI Library | @future/ui core set | Button · Input · Textarea · Alert · Skeleton · Spinner · Dialog · Drawer · Card · Table · DataTable · Dropdown · Select · Tabs · Tooltip · Badge | FE | 5 | 8 | H | FS#1 | S1 | Storybook-documented; a11y audit clean; variants map to design tokens
W-F04 | Layout | @future/app-layout | AppLayout · SidebarProvider · SidebarRenderer · NavbarRenderer · NavGroup static/dynamic · PermissionProvider | FE | 4 | 7 | H | FS#1 | S1 | Zones mount AppLayout with their own navigation config; static vs dynamic NavGroup enforced (no dual-shape)
W-F05 | Auth (FE) | Session hydration | httpOnly cookie read · session context · redirect-to-shell on 401 · token-aware tRPC client | FE | 2 | 3 | H | FS#1 | S1 | Unauth user bounced to shell; session context stable across route changes
W-F06 | Permissions (FE) | Permission-aware rendering | useCanAccess hook · PermissionContext hydration from kernel.getMyPermissions · permission-filtered NavGroups | FE | 2 | 3 | H | FS#1 | S1 | Unauthorized nav items hidden; denied routes render 403 card
W-F07 | Theming | Theme toggle + next-themes | Toggle component · next-themes integration · cookie persistence · system-preference default | FE | 1 | 2 | H | FS#1 | S2 | Toggle cycles light/dark/system without FOUC; persists across sessions
W-F08 | Notifications (FE) | In-app notifications popover | Real popover · unread count · mark-as-read · SSE transport | FE | 3 | 5 | M | FS#1 | S2 | Live events surface in popover; click-to-read; popover respects viewport
W-F09 | Data | tRPC client + query cache | Shared tRPC client typing across zones · React Query wrapper · cache keys convention · optimistic update helpers | FE | 3 | 5 | H | FS#1 | S1 | Any zone's tRPC client is typed end-to-end; optimistic mutation helpers documented
W-F10 | SSE | Streaming client primitive | EventSource wrapper · auto-reconnect · auth header propagation · used by notifications + AI streaming | FE | 2 | 3 | M | FS#1 | S2 | Reconnects on drop; headers survive refresh; unit tested against mock server
W-F11 | Zones | Zone scaffolding generator | turbo gen template producing layout · layout-client · navigation · proxy · minimal routes | FE | 2 | 3 | H | FS#1 | S1 | turbo gen workspace creates runnable zone matching pattern
W-F12 | Responsive | Responsive + mobile | Sidebar collapse · responsive grid · viewport-aware dialogs/drawers · tablet + small-desktop breakpoints | FE | 3 | 5 | M | FS#1 | S3 | Mobile / tablet visual QA across zones; touch targets ≥44px
W-F13 | QA | Storybook + visual regression | Storybook · visual regression baseline · axe a11y audit | FE | 2 | 4 | H | FS#1 | S2 | Storybook deployed to internal URL; visual-regression baseline green
W-F14 | Commons | Shared FE utilities | Date / time formatters · currency · permissions hook · toast abstraction · form helpers | FE | 2 | 3 | H | FS#1 | S1 | Utilities unit-tested; consumed by at least 2 zones
W-F15 | Forms | Form primitives | Form · FormField · react-hook-form integration · zod schema resolver · error-state helpers · async-validation pattern | FE | 3 | 5 | H | FS#1 | S1 | Forms compose across zones; validation messages consistent; optimistic submit + rollback on error
W-F16 | DateTime | Calendar + DatePicker | Calendar component · DatePicker · DateRangePicker · time-zone-aware formatting · keyboard a11y | FE | 2 | 4 | M | FS#1 | S2 | Planner Schedule view uses primitive; a11y audit clean; touch-friendly on tablet
W-F17 | FileUpload | File upload primitive | Drag-drop zone · S3 presigned upload flow · progress bar · cancel · mime-type + size guards | FE | 2 | 4 | M | FS#1 | S2 | Uploads round-trip to S3; cancel aborts mid-upload; Planner evidence consumes this primitive
W-F18 | Rich text | Lightweight rich-text input | Bold · italic · lists · links · markdown-serialised on submit; bounded by DESIGN.md | FE | 2 | 4 | M | FS#1 | S2 | Comments / evidence notes use primitive; serialised markdown round-trips; no XSS surface
W-F19 | Charts | @future/charts ECharts wrapper | Typed wrapper over ECharts · common chart shapes (bar · line · donut) · themed from design tokens · snapshot-ready for server-rendered charts | FE | 2 | 4 | H | FS#1 | S2 | Planner Charts view consumes primitive; themes match dark + light; SSR snapshot for digest email works
Core AI Agent (horizontal · Phase 1 W1–W4 · Phase 2 W5–W8)
ID | Phase | Module | Function | Feature | Layer | Effort Low | Effort High | Confidence | Owner | Sprint | Acceptance
W-A01 | 1 | LLM Client | Provider wrapper | Vercel AI SDK + OpenAI · model selector (gpt-5.4-nano classify, gpt-5.4 reason, text-embedding-3-small) · retry/backoff · token accounting | AI | 3 | 5 | H | AI Eng | S1 | Prompt round-trips; cost per call captured; provider swap is a one-file change
W-A02 | 1 | Prompt Store | Prompt management | Versioned templates in DB · env override · test fixtures | AI | 3 | 5 | M | AI Eng | S1 | Prompt change is a migration; every LLM call references a version in its trace
W-A03 | 1 | Confidence | Scoring framework | Derivation rules trace → H/M/L · exposure to HITL routing · drift harness | AI | 4 | 6 | L | AI Eng | S2 | Confidence band on every proposal; baseline eval passes
W-A04 | 1 | HITL | Routing engine | Routing matrix (proposal type → reviewer role) · fallback · review window · auto-expiry · backlog alert | AI | 4 | 7 | M | AI Eng | S2 | Routing tested against full role matrix; expiry hooks fire
W-A05 | 1 | Tools | Tool + MCP registry | Bounded registry · introspection via tRPC meta · enable/disable per agent | AI | 3 | 5 | M | AI Eng | S1 | Registry enumerates tools; permissions enforced at registration
W-A06 | 1 | Tools | ToolGateway pipeline | 10-step pipeline: auth · permission · taint · rate · budget · args-validate · execute · sanitize · log · trace | AI | 5 | 8 | M | AI Eng | S2 | Unauthorised tool call denied with audit; taint flows end-to-end; sanitisation drops disallowed fields
W-A07 | 1 | Runner | Sub-agent runner pattern | Base runner · prompt rendering · tool-calling loop · max-steps · safety ceiling · SSE events | AI | 4 | 6 | M | AI Eng | S2 | Base runner executes a canned agent; loop terminates at max-steps; SSE contract stable
W-A08 | 1 | Observability | Langfuse telemetry | Span creation · OTel integration · cost tag · prompt-version tag · trace-sampling policy | AI | 2 | 4 | H | AI Eng | S1 | Every LLM + tool call appears in Langfuse; trace navigable end-to-end
W-A09 | 1 | Streaming | SSE contract | Stream event types (token · tool-call · tool-result · finish · error) · backpressure · cancel token | AI | 2 | 3 | M | AI Eng | S2 | Stream events parse round-trip; cancel aborts upstream; backpressure handled
W-A10 | 2 | Security | Prompt-injection defence | Tenant-authored-text redaction · delimiter strategy · injection regression suite | AI | 3 | 5 | L | AI Eng | S3 | Adversarial prompts trigger refusal; regression suite gates CI
W-A11 | 2 | Security | Permission enforcement at AI boundary | Result-fetch permission check · structured-query permission audit · composition-derived disclosure guard | AI | 4 | 7 | L | AI Eng | S3 | Penetration test returns zero permission-leak incidents
W-A12 | 2 | Router | Free-form query router | Router · multi-sub-agent fan-out · synthesizer · disambiguation UX · query-preview contract | AI | 5 | 9 | L | AI Eng | S3–S4 | Baseline 30-query eval ≥80% first-attempt correctness
W-A13 | 2 | Cost | Cost metering + budget + circuit breaker | Per-user + per-tenant meter · budget service · circuit-breaker on breach · admin budget dashboard | AI | 3 | 5 | M | AI Eng | S4 | Per-tenant daily budget blocks excess; breaker short-circuits on breach; dashboard surfaces remaining budget
W-A14 | 2 | Quality | Prompt tuning + eval CI | Eval dataset · CI regression gate · Langfuse eval wiring | AI | 3 | 5 | M | AI Eng | S4 | Eval runs on every prompt change; regression blocks merge
Planner (vertical · integrates all three Core horizontal slices)
Every feature shows which layer(s) it spans. Most Planner rows are BE+FE; transcript + HITL + conversational features are BE+FE+AI.
ID | Module | Function | Feature | Layer | Effort Low | Effort High | Confidence | Owner | Sprint | Acceptance
W-P01 | Action | Domain model | Action aggregate · status lifecycle (Open → InProgress → Done → Blocked; Cancelled) · priority · stakes · project tag · deadline · owner · delegator · visibility scope · source | BE | 3 | 5 | H | FS#1 | S1 | Aggregate invariants tested; state transitions exhaustively covered
W-P02 | Action | CRUD handlers + tRPC | Create · update · delete · list · filter · paginate | BE | 3 | 5 | H | FS#1 | S1 | tRPC contract exercised by integration tests; permission-filtered lists verified
W-P03 | Action | UI | Action create / edit / view modal or drawer; unified UX for manual, AI-proposed, MS-Planner-synced actions | FE | 4 | 6 | H | FS#1 | S1 | UI indistinguishable across action sources; autosave on edit; keyboard a11y
W-P04 | Action | Evidence + attachments | Evidence CRUD (note + files + links) · S3 presigned upload · required when stakes=high and status=Done | BE+FE | 3 | 5 | H | FS#1 | S1 | Upload round-trips to S3; stakes=high gate enforced
W-P05 | Action | Comments | Comment thread on action · mention suggestions · email-out on new comment | BE+FE | 2 | 4 | H | FS#1 | S1 | Thread renders; mention triggers notification; delete requires audit
W-P06 | Plan | Plan / Project CRUD | Plan create · member management · label management · bucket management · ordering | BE+FE | 4 | 6 | H | FS#1 | S1 | Plan CRUD exercised; membership changes audited
W-P07 | Action | Views | Board view (drag-drop across buckets + status) · Grid view (inline editing) · Schedule view (week/month) · Charts view (progress donut, priority bar, bucket bar, workload by assignee) | FE | 6 | 10 | H | FS#1 | S1–S2 | Each view passes visual QA; filters persist in URL; group-by switch without reload
W-P08 | Personal | Personal Hubs | My Plans · My Tasks · My Day with carry-over; personal dashboard (open · overdue · completed · waiting-on) | BE+FE | 4 | 6 | H | FS#1 | S1 | Carry-over suggests yesterday unfinished; dashboard counts match filters
W-P09 | Meetings | Meetings list + detail | List of user's attended / organised meetings · detail page with transcript view and linked actions | BE+FE | 4 | 6 | M | FS#1 | S2 | List scoped to attendance / organising; detail page links actions; transcript visibility follows attendance policy
W-P10 | Meetings | On-demand extraction | "Extract actions with AI" button · rate-limited (default 10/hour) · surfaces proposals to HITL queue | BE+FE+AI | 3 | 5 | M | FS#1 | S2 | Button triggers Agent ingestion job; rate-limit enforced; proposals appear in queue
W-P11 | Agent Integration | Transcript webhook handler | MS Graph change-notification subscription for transcripts · webhook validation · metadata capture · ingestion job trigger | BE | 4 | 7 | L | FS#2 | S2 | Subscription renewed ahead of expiry; webhook validates MS challenge; ingestion job receives meeting + transcript
W-P12 | Agent Integration | Planner-domain sub-agent | Domain sub-agent using Core AI runner · read-only tool set (list meetings, list actions, fetch transcript excerpt, create proposal) · extraction prompt · confidence-scored output | BE+AI | 5 | 9 | M | AI Eng | S2 | Sub-agent ingests transcript and emits proposal matching HITL schema; trace visible in Langfuse
W-P13 | HITL | Proposal domain model | Proposal aggregate (proposed op · AI reasoning · transcript excerpt · confidence · status · expiry · routed-to) · per-capability audit | BE | 3 | 5 | H | FS#1 | S2 | Aggregate covers all proposal types; expiry job auto-cancels
W-P14 | HITL | Review queue UI | Proposals list · detail · accept / edit-and-accept / reject · unassigned-owner assignment · bulk-reject | FE | 5 | 8 | M | FS#1 | S2 | End-to-end flow round-trips to Agent; routing matrix displayed per proposal
W-P15 | HITL | Routing integration | Wire Planner proposals into Core AI HITL routing engine · fallback to meeting organiser · Admin backlog alerts | BE+AI | 2 | 4 | M | AI Eng | S2 | Routing matches BRD role matrix; 7-day auto-expiry; backlog notification fires
W-P16 | Agent Integration | Autonomous reminders | Deterministic 3-day / 1-day / overdue reminder emails to action owner · per-capability kill-switch aware | BE | 2 | 4 | H | FS#2 | S2 | Reminder scheduler fires on schedule; kill-switch stops reminders without removing job
W-P17 | Agent Integration | Escalation engine | AI-drafted escalation emails · HITL approval before send · route to line manager · suppresses reminder noise | BE+AI | 3 | 5 | M | AI Eng | S3 | Escalation drafted; reviewer approves; line manager receives exactly one message
W-P18 | Agent Integration | Anomaly detection + auto-pause | Threshold-based anomaly detector · auto-pause on trip · admin resume only | BE | 2 | 4 | M | FS#2 | S3 | Anomaly threshold trips pause; admin resume restores; audit trail complete
W-P19 | MS Sync | Microsoft Planner bidirectional sync | Admin OAuth · plan discovery · Future→MS push · MS→Future polling · eTag conflict detection · last-write-wins on title/status/deadline · scope limited to Admin-designated plans | BE | 8 | 14 | L | FS#2 | S3–S4 | Round-trip latency ≤5 min; deletion marks Cancelled; 429 backoff respects headers
W-P20 | Aggregated Views | Team + Manager views | Team health · Manager drill-down enforcing P2 · completion trend (4 weeks) · overdue-per-owner bar · line-manager + tech-lead variants | BE+FE | 6 | 10 | M | FS#1 | S3 | Drill-down respects reporting chain; no cross-hierarchy bypass; charts from live data
W-P21 | Aggregated Views | PMO + Account Manager views | PMO cross-portfolio (overdue rate by project / team / account; 12-week completion trend) · Account Mgr per-account view | BE+FE | 5 | 9 | M | FS#1 | S3 | PMO sees portfolio; Account Mgr sees per-account exposure; transcript access gated by attendance
W-P22 | Executive Digest | Weekly email | Monday-morning email: 5 numbers + 3 lists · 60-second phone-first readability · scheduler job · template · dry-run to sponsor | BE | 3 | 5 | H | FS#2 | S4 | Dry-run lands before pilot; phone render verified; unsubscribe respected
W-P23 | Admin Console | Scope + role + kill config | Auto-capture scope config · role assignment · per-capability kill switches · rate-limit config · anomaly thresholds · proposal-expiry window | BE+FE | 6 | 10 | M | FS#1 | S2 | Admin toggles reflect in agent within 60s; scope change audited
W-P24 | Admin Console | HITL queue backlog + audit view | System health: queue depth · proposals nearing expiry · agent status · capture scope summary · cross-hierarchy raw-access log | BE+FE | 4 | 6 | M | FS#1 | S3 | Dashboard reflects live data; cross-hierarchy access queryable with reason
W-P25 | Conversational AI | Query UI | Natural-language input · structured-query preview · result render (conversation + filtered view) · rate-limit surface · session-scoped history | FE | 4 | 7 | M | FS#1 | S4 | Query preview shown before execute; rate-limit enforced; session history not persisted across sessions
W-P26 | Conversational AI | Planner query executor | Safe query generation from structured intent · permission enforcement at result-fetch · scope restricted to actions + meetings | BE+AI | 5 | 9 | L | AI Eng | S4 | Adversarial queries return permission-denied correctly; result count matches UI lists
W-P27 | Conversational AI | Prompt tuning + eval | Planner-specific eval dataset (30 queries across roles) · first-attempt correctness ≥80% gate | AI | 3 | 5 | M | AI Eng | S4 | Eval gate green on baseline set; drift monitored via Langfuse
W-P28 | Notifications | Lifecycle notifications | Email + in-app for assignment · completion · comment · overdue · escalation-approved | BE+FE | 3 | 5 | H | FS#2 | S2 | Each event triggers exactly one recipient-scoped notification; in-app popover shows unread
W-P29 | Data retention | Admin deletion + export | Admin-initiated action / transcript / evidence deletion · deletion logged with reason · export-on-request hook | BE+FE | 2 | 4 | H | FS#2 | S4 | Deletion removes rows and logs; export endpoint returns tenant-scoped archive
W-P30 | Pilot readiness | Pilot measurement instruments | Time-diary template · baseline + week-4 interview scripts · conversational-query review rubric · BA capture ground-truth guide | — | 2 | 3 | H | BA | S4 | Instruments ready by pilot Day 1; reviewed with PM and BA
Cross-cutting workstreams (non-build, recurring)
Not code deliverables but required for delivery. Owned by the non-builder roles (PM, PO, SM, BA, QA). Effort shown as range × 8 build weeks + 4 pilot weeks.
ID | Workstream | Function | Feature | Layer | Effort Low | Effort High | Confidence | Owner | Sprint | Acceptance
W-PM01 | PM | Project governance | Project Plan authoring + Kickoff pack + track-lead confirmation + Open Question closure | — | 3 | 5 | H | PM | S1 | Workbook signed by Sponsor at M00; track leads named in 06-Resources
W-PM02 | PM | Delivery tracking | Weekly status report · milestone + risk updates on this workbook · sprint review demo coordination | — | 2 | 3 / week × 8 | H | PM | All | Report delivered each Friday; RAG status matches WBS state
W-PM03 | PM | Scope + CR management | CR intake, impact analysis, rebaseline updates · scope veto | — | 0.5 | 1 / week × 8 | H | PM | All | Every scope change has a CR row on 03-Scope Block 5
W-PM04 | PM | Stakeholder communication | Sponsor sync · BOD weekly sync · Steering Committee preparation | — | 1 | 2 / week × 12 | H | PM | All + Pilot | Meetings held on cadence; decisions captured
W-PM05 | PM | Pilot launch + rollout comms | Pilot comms pack · launch note · post-pilot decision memo · wave rollout playbook | — | 3 | 5 | M | PM | Pilot + Wave | Pilot comms pack approved by Sponsor pre-M04
W-PO01 | PO | Product ownership (dual-hatted Sponsor) | Refinement representation · story acceptance at sprint review · Definition of Success sign-off | — | 2 | 3 / sprint × 4 | H | PO (Hung Vu) | All | Every story accepted or rejected at sprint review; DoS quadrants signed off
W-SM01 | SM | Ceremonies | Daily stand-up · sprint planning · sprint review · retro facilitation · impediment log | — | 1 | 2 / day × 40 | H | SM | All | Ceremonies held to time; impediments closed or escalated within SLA
W-SM02 | SM | Velocity + burn-down | Velocity tracking · burn-down chart · sprint health signal | — | 0.5 | 1 / sprint × 4 | H | SM | All | Velocity chart populated on 05-Approach Block 7 at every sprint end
W-BA01 | BA (MVP) | Requirements + stories | User-story refinement · acceptance-criteria drafting with PM + PO · requirement traceability into acceptance criteria of each WBS row | — | 4 | 6 | H | BA | S1 | Every WBS W-P* row has a corresponding story with AC and measurable output; DoR met before sprint planning
W-BA02 | BA (MVP) | UAT + pilot rehearsal | UAT scripts · pilot rehearsal scripts · ground-truth corpus plan | — | 3 | 5 | M | BA | S3–S4 | UAT scripts executable against staging build; rehearsal passes pre-M04
W-BA03 | BA (MVP) | Pilot measurement instruments | Time-diary template · interview scripts (IC · TL · PM · AM · LM · PMO · Exec) · conversational-query review rubric · ground-truth extraction guide | — | 3 | 5 | M | BA | S4 | Instruments ready by pilot Day 1; reviewed with PM
W-BA04 | BA (MVP) | Pilot execution | Baseline time-diary week · week-4 interviews (15-20 users) · ground-truth extraction on ~12-20 sampled meetings (G4) · synthesis | — | 10 | 15 | M | BA + Pilot Team Lead | Pilot W1-W4 | Interview outputs synthesised · G1–G7 outcome values computed · kill-criteria inputs on 09-ExecSupport
W-BA05 | BA (legacy) | Legacy systems discovery | Stakeholder mapping · weekly interviews per legacy system (EMS · Timesheet · Hiring · Resource Insight) · per-system requirement briefs feeding future Future modules | — | 2 | 4 / week × 12 | M | BA | All + Pilot | Per-legacy-system requirement brief authored and shared with future-module owners
W-QA01 | QA | Test strategy + plan | Test plan for Planner MVP · test data fixtures · environment setup · exit-criteria gating | — | 2 | 4 | H | QA | S1 | Test plan reviewed with Tech Lead · fixtures load in staging
W-QA02 | QA | Automated suite | E2E Playwright critical flows · integration suite orchestration · visual regression baseline | — | 4 | 7 | M | QA | S2–S3 | Critical flows pass in CI · baseline images approved
W-QA03 | QA | Adversarial / security | Adversarial prompt suite for Core AI Phase 2 · penetration-style test for conversational AI (REQ-22g) · security scan gating | — | 4 | 6 | L | QA + AI Eng | S3–S4 | Zero permission-leak incidents pre-M04; scan clean
W-QA04 | QA | Performance | Load test on hot endpoints · Graph API rate-limit simulation · sync-latency budget | — | 2 | 3 | M | QA + SRE | S4 | Targets met pre-M04 · SLO dashboards live
W-QA05 | QA | Defect management | Defect intake · triage · closure tracking · leakage-rate metric | — | 0.5 | 1 / week × 8 | H | QA | All | Defect leakage < 5% at pre-pilot gate
W-QA06 | QA | Pre-pilot rehearsal | Rehearsal execution · exit-criteria sign-off · pilot go/no-go recommendation | — | 2 | 4 | H | QA + BA + PM | S4 | ≥95% rehearsal pass; PM go/no-go documented
W-OP01 | DevOps | Infrastructure as code | Terraform modules for AWS (VPC · ECS · ECR · RDS · ALB · CloudFront · WAF · Secrets Manager) · dev + single pilot-staging env only — no production env in this MVP | — | 3 | 5 | M | DevOps + FS#2 | S1 | terraform plan clean on both envs; dev + staging stood up end of S1; staging is the pilot-running env
W-OP02 | DevOps | CI pipeline | GitHub Actions · Turborepo remote cache · lint · unit · integration (testcontainers) · build ARM64 image · SAST · SBOM · Cosign sign · push to ECR | — | 3 | 5 | H | DevOps + FS#2 | S1 | PR-to-merge full pipeline runs in < 15 min; ARM64 image published on main
W-OP03 | DevOps | CD pipeline | Staging deploy on main merge · ECS rolling deploy · auto-rollback on health-check failure. No production deploy in this MVP — pilot runs on staging. | — | 2 | 4 | H | DevOps + FS#2 | S2 | Staging deploys on every merge; rollback proven via a canary-failure drill on staging
W-OP04 | DevOps | Monitoring & alerting | SLO dashboards (CloudWatch + Langfuse) · Sentry for FE · alert routes (Slack + email) · on-call rotation for pilot window | — | 2 | 4 | M | DevOps + SRE | S3 | Dashboards live; alerts fire on synthetic error; on-call rotation published
W-OP05 | DevOps | Release runbook | Runbook · rollback procedure · smoke-test script · DB migration order · feature-flag cutover playbook | — | 2 | 3 | H | DevOps + PM | S4 | Runbook exercised end-to-end in pilot rehearsal; rollback drill timed under 15 min
W-OP06 | DevOps | Secrets + config | AWS Secrets Manager provisioning · OpenAI key · MS Graph app credentials · SES credentials · Langfuse keys · rotation policy | — | 1 | 2 | H | DevOps + IT | S1 | All secrets loaded from Secrets Manager; no plaintext in env files or repo
W-OP07 | DevOps | Performance + load prep | Load-test harness (k6) · connection-pool sizing per env · RDS instance right-sizing pre-pilot | — | 2 | 3 | M | DevOps + SRE + QA | S4 | Load tests pass at 2× expected pilot concurrency; RDS headroom ≥30%
W-OP08 | DevOps | Post-deploy verification | Automated smoke tests on staging after each deploy · health-check endpoints · synthetic user journey run hourly during pilot | — | 2 | 3 | M | DevOps + QA | S4 | Smoke tests run automatically post-deploy on staging; synthetic journey green for 2 hours before pilot start
Rollup totals (indicative)
• Core BE (W-B01..W-B21): ~51–82 MD · average ~67 MD
• Core FE (W-F01..W-F19): ~47–81 MD · average ~64 MD
• Core AI (W-A01..W-A14): ~48–80 MD · average ~64 MD
• Planner (W-P01..W-P30): ~113–191 MD · average ~152 MD
• Grand total: ~259–434 MD · midpoint ~348 MD
Capacity check
Available builder-MD over the 8-week build window, after deducting ~3 VN holiday days in Sprint 1:
• FS#1 (Planner FE + Core FE): ~38 working days × 1 FTE = 38 MD
• FS#2 (Planner BE + Core BE): ~38 MD
• AI Engineer (Core AI + Planner Agent integration): ~38 MD
• Combined builder capacity: ~114 MD
Planned midpoint work ≈ 348 MD against ~114 MD capacity ⇒ ~3.1× over. Resolution paths (pick two):
• Push Admin console, MS Planner sync, Phase 2 Core AI security-plus-router features to post-pilot (after W8, during wave phase).
• Reduce Planner aggregated views to Team + PMO only (drop Account Manager + Line Manager differentiation until post-pilot).
• Scope the conversational AI to pre-built query cards only for MVP; free-form router lands in Phase 2 but is not gated on W8.
• Data Engineer onboarding pulls Aggregated Views infrastructure work off FS#2's plate.
Recommendation: adopt (1) + (3) + aim for (4); confirm at Kickoff and capture as CRs if scope needs rebaselining.
Block 2 — In Scope
• Microsoft 365 SSO login via Entra ID (Core BE + Core FE handshake).
• Manual action CRUD with full lifecycle, priority, stakes, project tag, deadline, owner; shared data model for AI-proposed and MS-Planner-synced actions (unified UX).
• Personal action list, personal dashboard, My Day / My Tasks / My Plans hubs.
• Plan / project CRUD, membership, labels, buckets.
• Action views: Board, Grid, Schedule, Charts (pre-built chart set per BRD §6.1.8).
• Evidence, attachments, comments on actions.
• Meetings page: list of user's attended / organised meetings, transcript viewer, linked actions, on-demand AI extraction (rate-limited).
• HITL review queue with accept / edit-and-accept / reject and unassigned-owner routing.
• Aggregated views: Team health, Manager drill-down, Account Manager, PMO portfolio, Admin system health.
• Executive weekly digest email.
• Microsoft Planner bidirectional sync on title / status / deadline for Admin-designated plans.
• Conversational AI query interface — read-only, session-scoped, permission-enforced.
• Admin console: scope config, role assignment, kill switches, rate limits, anomaly thresholds, proposal expiry, backlog view, audit-log view.
• Notifications: email + in-app for lifecycle events; deterministic 3-day / 1-day / overdue reminders.
• Agent behaviours: auto-capture within configured scope, AI extraction to HITL proposals, proposal expiry, anomaly detection with auto-pause, kill-switch surface.
• Core Backend: monorepo scaffolding, Entra ID SSO primitive, magic-link primitive, org-chart permissions engine, audit log, RLS, outbox + relay, pg-boss, MS Graph adapter scaffolding, outbound email gateway, observability, rate limiter + kill switches, shared BE commons.
• Core Frontend: Next.js multi-zone, design system tokens + Tailwind, @future/ui, @future/app-layout, theme toggle, notifications popover, responsive layouts, zone scaffolding generator, shared tRPC client + React Query, SSE client primitive, Storybook + visual regression, shared FE commons.
• Core AI Agent Phase 1: LLM client, prompt store, confidence scoring, HITL routing engine, tool/MCP registry + ToolGateway, sub-agent runner, SSE contract, Langfuse telemetry.
• Core AI Agent Phase 2: prompt-injection defence, permission enforcement at AI boundary, free-form query router, cost metering + budget + circuit breaker, prompt tuning + eval CI.
Block 3 — Out of Scope
• Custom chart builder, user-selected metrics / dimensions, AI-generated charts from natural language. Pre-built chart set only in this MVP. Analysis module delivers these later.
• Write operations via conversational interface (query-only for this release).
• Mobile-native application (desktop web only; responsive where feasible).
• Vietnamese language UI (English only for this release).
• Inbound email parsing (actions@seta-international.vn mailbox).
• Capture from non-Teams meetings (hallway, phone, in-person).
• Integration with Microsoft Lists, Loop, Power Automate.
• External BI integration (Power BI, Tableau).
• Direct audio recording or transcription (Agent consumes text transcripts only).
• Transcript editing by users (Microsoft Teams remains the source of truth).
• Fully autonomous AI (tiered HITL is architectural, not a temporary constraint).
• Commercialisation or multi-tenant SaaS packaging.
• Formal uptime SLA with credits.
• Features added via CR post-kickoff (tracked separately in Block 5 of this sheet).
• Production environment. Only a single pilot-staging env is provisioned in this MVP; the pilot itself runs on staging. Production environment (with scaling, DR, backup windows, blue-green deploys) is a post-pilot scope item before Wave 1 rollout.
Block 4 — Change Request (CR) Process
• Submit CR. Requester completes CR form; assigned CR ID.
• Impact Analysis. Track lead + PM assess scope / time / cost / risk.
• Approval. CCB (Sponsor + PMO + CTO) or PM (under veto authority) approves.
• Re-baseline. WBS, timeline, acceptance weights updated on this workbook.
• Execute. Work performed; CR row status updated until closed.
Rule: No CR = No work. Every change must be traceable (ID, owner, date, decision).
Block 5 — CR Log
CR ID | Description | Impact (Scope / Time / Cost) | Decision | Status
CR-000 | Template row — delete when first real CR lands | — | — | —

## 04-Timeline
Sheet: 04-Timeline
PPTX Slides 11-12. Master timeline · Milestone tracking · Sprint plan · Status legend · Holiday calendar.
Block 1 — Master Timeline (week-by-week band chart)
Render as a Gantt-style band chart in Excel (one row per workstream; horizontal bands coloured by phase). Below is the ASCII preview for transcription.
Week W1 W2 W3 W4 W5 W6 W7 W8 ¦ W9 W10 W11 W12 ¦ Waves ... Calendar (approx) 22-Apr 06-May 20-May 17-Jun ¦ Pilot (4w) ¦ Kickoff ■ Core BE foundations ███████ Core FE foundations ███████ Core AI Phase 1 ███████ Planner core build ████████████████ Core AI Phase 2 ███████████████ Planner MVP polish ███████ MS Planner sync ███████████ Conversational AI ███████ Integration + pilot rehearsal ███ Pilot █████████████ Pilot-to-Wave gate ■ Wave 1 (TBD) ████ Full-coverage (TBD) ████ Post-rollout review ■
Legend:
• ■ = milestone day
• █ = active work band
Block 2 — Milestone Tracking
Updated weekly. Planned dates are calendar-aligned; Actual captured when event occurs. Status uses Block 4 legend colouring.
ID | Milestone | Planned | Actual | Status | Notes
M00 | Kickoff | Wed 22 Apr 2026 |  | Planned | Project Plan v1.0 signed; track leads confirmed; open questions closed
M01 | Core Foundations ready | Tue 05 May 2026 (W2 end) |  | Planned | Monorepo · identity · permissions · audit · RLS · outbox · design tokens · AI Phase 1 scaffolding
M02 | Core AI Agent Phase 1 complete | Tue 19 May 2026 (W4 end) |  | Planned | LLM client + prompt store + confidence + HITL routing + tool registry + Langfuse
M03 | First Working Version | Tue 19 May 2026 (W4 end) |  | Planned | Internal demo to sponsor + CTO
M04 | MVP Pilot-ready | Tue 16 Jun 2026 (W8 end) |  | Planned | Full Planner feature set · MS Planner sync · conversational AI · digest · pilot measurement instruments
M05 | Core AI Agent Phase 2 complete | Tue 16 Jun 2026 (W8 end) |  | Planned | Prompt-injection defence · permission boundary · router · cost meter · eval CI
M06 | Pilot-to-Wave gate | Tue 14 Jul 2026 (W12 end) |  | Planned | Outcome measures + kill-criteria review; Steering Committee decision
M07 | Wave 1 complete | TBD |  | Planned | First department wave (~2 weeks)
M08 | Full-coverage rollout | TBD |  | Planned | All target users live
M09 | Post-rollout review | TBD |  | Planned | Committee review; next module scoped
Block 3 — Sprint Plan
4 sprints × 2 weeks for build; pilot + rollout tracked as milestone rows rather than sprints. Working Days column nets VN public holidays.
Sprint | Start | End | Working Days | Goal | Scope summary | Deliverable | Exit Criterion | Status
S1 | Wed 22 Apr 2026 | Tue 05 May 2026 | 7 (3 days lost to VN holiday, see Block 5) | Core foundations + Planner core scaffold | Core BE monorepo + identity + permissions + audit + RLS + outbox; Core FE multi-zone + @future/ui core + @future/app-layout; Core AI Phase 1 LLM client + prompt store + tool registry + Langfuse; Planner action domain + CRUD handlers + basic UI | Foundations demo: user signs in, creates an action, sees it on a list | Core smoke tests green; all three Core tracks boot together in dev; Planner CRUD end-to-end works | Planned
S2 | Wed 06 May 2026 | Tue 19 May 2026 | 10 | First Working Version + Core AI Phase 1 complete | Planner views (Board/Grid/Schedule/Charts) · Personal Hubs · Meetings page shell · HITL queue UI · Teams transcript webhook · Planner-domain sub-agent · confidence + routing · admin console scope config · notifications · theme toggle | M02 + M03: demoable First Working Version | M02 + M03 acceptance criteria (02-Contract Block 2) green; internal demo passes | Planned
S3 | Wed 20 May 2026 | Tue 02 Jun 2026 | 10 | Feature completion + Phase 2 security | Aggregated views (Team + PMO first) · MS Planner sync (OAuth + discovery + push) · escalation engine · anomaly detection · Core AI Phase 2 prompt-injection defence + permission enforcement · responsive layouts | All non-MVP-critical polish items deferred to S4 | Aggregated views deliver for pilot-relevant roles; MS sync round-trips title/status/deadline | Planned
S4 | Wed 03 Jun 2026 | Tue 16 Jun 2026 | 10 | MVP Pilot-ready + Core AI Phase 2 complete | Conversational AI (router + eval CI) · cost metering · executive digest · retention/deletion · pilot measurement instruments · final security testing · integration + stabilisation + pilot rehearsal | M04 + M05: pilot-ready | Pre-pilot gate green on Definition of Success (05-Approach Block 12); no critical bugs; penetration test returns zero permission-leak incidents | Planned
Pilot | Wed 17 Jun 2026 | Tue 14 Jul 2026 | ~18 (BA + PM running measurement) | Pilot operations + outcome measurement | Live pilot · outcome measures (G1–G7) · weekly health checks · BA conducts interviews + time diary | Pilot gate decision | Kill-criteria review clean; Steering Committee decision recorded (M06) | Planned
Wave 1 | TBD | TBD | — | First rollout wave | IT + PMO-coordinated rollout to first department | Wave health report | No critical blockers; adoption metrics maintained | Planned
Block 4 — Status Legend (colour key)
Used across this sheet and the Milestone rows on 02-Contract.
Status | Colour fill (hex) | Description
On-track / Done | Green #16a34a | Trending to plan; no action needed
At risk / Slight delay | Yellow #eab308 | Within tolerance but needs attention; PM review
Blocked / Critical | Red #dc2626 | Off-track; escalation active
Planned | Grey #6b7280 | Future activity; not yet started
Done | Blue #2563eb | Completed and accepted
Apply to Status columns on 02-Contract Block 2, 04-Timeline Block 2 + 3, each Track-* sheet Sprint plan.
Block 5 — Holiday Calendar
VN public holidays across the W1–W12 build + pilot window, plus any other non-working dates that affect capacity.
Date | Day | Holiday | Working-day impact | Sprints affected
Mon 27 Apr 2026 | Mon | Hung Kings Commemoration (observed) | -1 | S1
Thu 30 Apr 2026 | Thu | Reunification Day | -1 | S1
Fri 01 May 2026 | Fri | International Labour Day | -1 | S1
Wed 02 Sep 2026 | Wed | National Day | -1 | Post-pilot wave phase
Total capacity deduction in Sprint 1 = 3 working days. Sprint 1 available = 7 working days per FTE instead of 10.
Reconfirm exact observed dates with the VN government labour announcement on file (HR to provide at Kickoff). Add any bridge days granted in that announcement.
Block 6 — QA + DevOps per-sprint activities
Overlay on the Sprint Plan (Block 3). Makes explicit what QA and DevOps owners deliver each sprint.
QA activities by sprint
Sprint | QA activities | Deliverable | Exit
S1 | Test strategy + plan · test-data fixtures · staging env setup · first unit + integration tests authored alongside Dev · defect-tracking rig live | Test plan signed off; fixtures load in staging; defect log live on 08-Risks-Issues | Test plan reviewed with Tech Lead
S2 | First Playwright e2e flows (sign-in · action CRUD · HITL review) · visual-regression baseline · integration suite coverage on Planner handlers | e2e suite in CI; visual baseline green | e2e critical flows pass on every main merge
S3 | Adversarial prompt suite for Core AI Phase 2 · composition-sensitivity tests · performance-test harness stood up | Adversarial suite in CI; k6 script running on staging | Red-team regression passes; perf dashboards live
S4 | Penetration-style test on conversational AI (REQ-22g) · pre-pilot rehearsal · pilot go/no-go recommendation · defect-leakage review | Pentest report; rehearsal pass; recommendation memo | Zero permission-leak incidents; ≥95% rehearsal pass; defect leakage < 5%
Pilot | Daily triage of pilot-reported issues · support-ticket quality review · post-pilot defect summary | Pilot issue log + severity-by-sprint report | Pilot-to-Wave gate (M06) input
DevOps activities by sprint
Sprint | DevOps activities | Deliverable | Exit
S1 | Terraform for dev + staging (VPC, ECS, ECR, RDS, ALB, CloudFront, WAF, Secrets Manager) · CI pipeline · secrets loaded · observability baseline | Dev + staging envs reachable; PR pipeline green | terraform plan clean; smoke-deploy to staging works
S2 | CD pipeline for pilot-staging · staging auto-deploy on merge · auto-rollback wired. No prod env in this MVP. | Staging deploys on every merge; rollback drill on staging | Canary-failure drill on staging proves rollback < 15 min
S3 | SLO dashboards · alert routes · on-call rotation scheduling · pre-pilot load test dry run | Dashboards live · alerts fire on synthetic error | First on-call handover rehearsed
S4 | Release runbook · load test at 2× pilot concurrency · post-deploy verification · secrets rotation review · backup + restore drill | Runbook exercised · load target met · backup/restore timed | Rollback + restore SOPs approved by CTO
Pilot | On-call coverage · daily health-check review · cost dashboard review · weekly rotation handover | On-call calendar · weekly cost report | No unresolved P1s carried > 24 h
Block 7 — Weekly Cadence Overview
Visible on one row per week for PMO at-a-glance view.
Week | Theme | Sprint | Key events
W1 (22 Apr) | Kickoff + foundations | S1 | Kickoff Wed; open-questions close Fri W1
W2 (29 Apr) | Foundations push (holiday-shortened) | S1 | M01 Core Foundations ready
W3 (06 May) | Feature build starts | S2 | Planner views + HITL queue wiring
W4 (13 May) | First Working Version | S2 | M02 + M03 demo to sponsor
W5 (20 May) | Aggregated views + MS sync | S3 | AI Phase 2 security begins
W6 (27 May) | Pilot team nomination | S3 | Pilot team + measurement instruments
W7 (03 Jun) | Conversational AI + digest | S4 | MVP polish
W8 (10 Jun) | Integration + pilot rehearsal | S4 | M04 + M05 pre-pilot gate
W9 (17 Jun) | Pilot begins | Pilot | Baseline measurements
W10 (24 Jun) | Pilot week 2 | Pilot | Mid-pilot check
W11 (01 Jul) | Pilot week 3 | Pilot | Interview scripts in use
W12 (08 Jul) | Pilot week 4 + gate | Pilot | M06 Pilot-to-Wave gate Tue 14 Jul

## 05-Approach
Sheet: 05-Approach
PPTX Slides 13-23. Largest sheet — 12 stacked blocks covering Org, R&R, Escalation, Communication, Stakeholder Matrix, Methodology + DoR/DoD, KPIs, Technical Approach, QA, CI/CD, AI Differentiator, Definition of Success.
Block 1 — Organisation Chart
Render as embedded shapes / image. Text preview:
Board / Steering Committee (Hung Vu — Sponsor & Product Owner · Thu Mai — CTO · Hoang Nguyen — PMO) ¦ Project Manager (Canh Ta) ¦ +-------------+-------------+----------+---------+------------+--------+ ¦ ¦ ¦ ¦ ¦ ¦ ¦ Product Scrum Business Tech Lead AI Engineer FS#1 FS#2 Owner Master Analyst (rotates) (full-stack) (full-stack) (Hung Vu) (owns assigned (owns assigned modules/ modules/ features) features)
Notes:
• Hung Vu is dual-hatted: Sponsor (CEO) and Product Owner. The PO role is embedded in the BOD; story acceptance at sprint review is Hung Vu's call.
• BOD triplet (Hung Vu + Thu Mai + Hoang Nguyen) meets weekly for a sync on status, scope, and risk (separate from the monthly Steering Committee formal session for gate decisions).
• PM reports to Sponsor; owns delivery accountability, backlog, and prioritisation.
• SM + BA are 50%-effort cross-cutting roles.
• FS#1 + FS#2 + AI Engineer form the builder core; Tech Lead hat rotates (typically FS#2 owns architectural decisions).
• Designer-Lead (Mia / Darcy) is borrowed from another project; owns three critical surfaces: HITL queue, aggregated dashboards, action detail view.
Block 2 — Roles & Responsibilities
Role | Responsibilities
PM | Overall delivery · backlog · prioritisation · scope (veto authority from Sponsor) · stakeholder communication · escalation · sprint planning chair
PO | Story acceptance at sprint review · user representation in refinement · ensures "did we build the right thing this sprint"
SM | Ceremonies · velocity tracking · blocker unblocking · retrospective facilitation · coaching on DoR/DoD
BA | Planner MVP: requirements · user stories · acceptance criteria · UAT design · pilot feedback coordination. Parallel stream: legacy systems discovery (stakeholder interviews · per-system requirement briefs feeding future Future modules). Flexible allocation between the two streams; PM covers capacity gaps.
Tech Lead | Architecture decisions · code review gatekeeper · tech-risk mitigation · cross-module contract adjudication (default-assigned to FS#2)
FS Dev #1 | Full-stack. Owns assigned Planner module features and Core-slice work end-to-end — BE, FE, and integration layers. Split of modules / features between FS#1 and FS#2 decided at Kickoff.
FS Dev #2 | Full-stack. Same framing as FS#1 — owns assigned modules / features end-to-end. No BE-vs-FE specialisation between the two devs.
AI Engineer | Core AI Agent Phase 1 + Phase 2 · Planner-domain Agent integration (transcript sub-agent, extraction prompts, conversational executor)
QA | Test plan · execution · defect tracking (shared across team with dedicated QA lead TBD at Kickoff)
DevOps / SRE | CI/CD · ECS deployments · observability alerts · release runbook (shared function)
Designer-Lead (borrowed) | HITL queue UX · aggregated dashboards UX · action detail view · design-system adherence reviews
Data Engineer | Core Data Platform (if onboarded by W1; otherwise this role's work is deferred post-MVP and aggregated views run on direct operational-DB queries)
Rule: Every task has exactly one Accountable on the RACI matrix (06-Resources Block 2). PM + PO roles are explicitly complementary, not overlapping.
Block 3 — Escalation Path + Response SLA
Escalation tiers
Level | Trigger | Action
L1 | Team blocker or daily issue | Track lead + SM resolve within 24 hours
L2 | Delay >3 days, multi-team issue, or cross-track dependency slip | PM escalates to Sponsor within 48 hours
L3 | Critical risk · scope/budget breach · pilot kill-criterion tripped | Steering Committee decides within 1 week
Response SLA
Severity | Response | Resolve
P1 — Critical (pilot-impacting or security) | 15 minutes | 4 hours
P2 — High (blocking pilot feature) | 1 hour | 1 business day
P3 — Medium (degraded behaviour, workaround available) | 4 hours | 3 business days
P4 — Low (cosmetic, nice-to-have) | 1 business day | Next release
Block 4 — Communication Plan
Ceremony / Meeting | Audience | Frequency | Duration | Owner | Output
Daily stand-up | Delivery team (PM, PO, SM, builders, designer) | Daily | 15 min | SM | Blockers, today's plan
Sprint planning | Delivery team + PO | Bi-weekly (sprint start) | 2 h | PM | Sprint backlog; exit criterion
Sprint review / demo | Delivery + stakeholders + PO | Bi-weekly (sprint end) | 1 h | PM + PO | Accepted / rejected stories; demo recording
Retrospective | Delivery team | Bi-weekly | 1 h | SM | Action items, filed as CRs or track-level tasks
BOD weekly sync | Hung Vu (Sponsor + PO) · Thu Mai (CTO) · Hoang Nguyen (PMO) · PM | Weekly | 30 min | PM | Status · scope changes · risks · BOD-level decisions needed
Steering Committee (formal) | BOD triplet + CTO + PMO + PM | Monthly (W4, W8, W12 gates) | 1 h | PM + Sponsor | Gate decisions (M03, M04, M06); budget / scope rebaselines
Weekly status report | All stakeholders | Weekly (written) | — | PM | Progress · RAG · risks · decisions needed
BA legacy-discovery interviews | Stakeholder representatives (per legacy system) | Weekly (parallel workstream) | 45 min × N | BA | Stakeholder notes; per-system requirement brief updates
HITL review queue daily digest | Meeting organisers + Admin | Daily email | — | System | Pending proposal count + expiry risk
Pilot measurement interview (post-launch) | BA + pilot team reps | One-off (pilot W4) | 20 min × 15-20 | BA + Pilot Team Lead | Interview transcript + outcome scores
Block 5 — Stakeholder Engagement Matrix
Place each stakeholder by influence (row) × interest (column). Cells name the strategy plus the named stakeholders.
| High Interest | Low Interest
High Influence | Manage Closely — Hung Vu (Sponsor), Thu Mai (CTO), Hoang Nguyen (PMO), Mia/Darcy (Designer-Lead) | Keep Satisfied — SETA Finance (budget watcher), IT Infrastructure lead
Low Influence | Keep Informed — Pilot team members, line managers of pilot users, PMO analyst, BA counterparts on future modules | Monitor — General SETA staff; non-pilot departments until Wave 1
Block 6 — Methodology & SDLC Governance
Methodology selected: Agile Scrum, 2-week sprints. Not Waterfall. Not Hybrid.
DoR / DoD per phase
Phase | Input | Output | Definition of Ready (DoR) | Definition of Done (DoD) | Owner
Analysis | Business need + BRD | User story with acceptance criteria | Stakeholder confirms problem; metric is quantifiable | Story has AC + effort estimate + sprint assignment | BA
Design | Story | High-level + low-level design; UX mockup | Scope signed-off in sprint planning | Tech-review passed; design token adherence verified | Tech Lead + Designer
Dev | Design + story | Code + unit tests + integration tests | Task ≤ 5 MD; one owner; AC is measurable | Test-first: test written and failing before code · ≥70% coverage (lines · functions · branches) · no tests/ dirs (tests co-located) · no Promise.all on DB queries in handlers · no .js extensions on relative imports · code review approved by Tech Lead or peer | Dev
QA | Build | Test report; defect list | Test plan approved; UAT environment reachable | 0 critical · ≤ 2 high with documented workaround · ≥ 95% test pass · coverage ≥ 70% · security scan clean | QA
UAT / Pilot rehearsal | Signed build | Pilot rehearsal sign-off | UAT env with realistic data; pilot playbook drafted | ≥ 95% pass on pilot rehearsal scripts; no blocker | PM + BA
Release | UAT sign-off | Pilot-staging deployment | Runbook ready; rollback plan in place | Smoke test passes; Langfuse + CloudWatch dashboards green for 2 hours on staging | DevOps
Block 7 — KPI Tracking Dashboard
Metric tiles (populated weekly)
Metric | Target | Week Value | Status
Progress (% of MVP scope delivered) | 100% by W8 | — | Planned
Defect rate (P1+P2 / total closed) | < 2% | — | Planned
Coverage (lines, functions, branches) | ≥ 70% per CLAUDE.md | — | Planned
Pilot CSAT (set at pilot W4) | ≥ 4 / 5 | — | Planned
Sprint Velocity
Captured at each sprint end. Populate post-S1.
Sprint | Planned story points | Delivered story points | Note
S1 | TBD (after planning) | — | 3-day holiday capacity hit
S2 | — | —
S3 | — | —
S4 | — | —
Burn-down
Populate at each daily stand-up. Use line chart on the workbook with remaining story points on the Y-axis and sprint day on the X-axis.
Block 8 — Technical Approach
Stack (card grid, 6 cards)
Card | Choice | Rationale
Frontend | Next.js 16 (multi-zones, 11 zones + shell) · TypeScript 6 · React 19 · Tailwind v4 · @future/ui (CVA-based) · next-themes | Multi-zone architecture isolates zone failures; Tailwind + design tokens enforce DESIGN.md discipline; zones fully autonomous
Backend | NestJS 11 modular monolith · Turborepo · tRPC 11 (end-to-end type-safe) · Hexagonal + DDD per module · Bun 1.3 runtime | One API service; cross-module communication via QueryFacade + domain events; no FK across schema boundaries; module autonomy
Database | PostgreSQL 16 · Drizzle ORM · schema-per-module · RLS on every tenant-scoped table · tenant_id mandatory · pgBouncer pool | Schema-per-module keeps boundaries; RLS prevents cross-tenant data escape by construction; pool-client-per-request enforced
Infrastructure | AWS ECS Fargate Graviton ARM64 · ECR · CloudFront · WAF · Secrets Manager · ap-southeast-1 region | ARM64 only for cost; Secrets Manager only for credentials; no console changes (Terraform only)
Observability | Langfuse (self-hosted ECS) for LLM traces · CloudWatch logs · Sentry for FE errors · OpenTelemetry for spans | Langfuse bridges LLM + tool + sub-agent traces; OTel + Langfuse unified through AI SDK wiring
Security | Zero-trust · Entra ID SSO · RLS + canDo + tRPC middleware · KMS-encrypted at rest · TLS in transit · SAST/DAST in CI · SBOM per image | Defence-in-depth; LLM outputs are never trusted to perform privileged operations
Jobs & events
• pg-boss for scheduled + triggered jobs (reminders, digest, sync polling, subscription renewal).
• outbox_event table + polling relay for cross-module events (zero-dependency plain-TS shapes in packages/event-contracts).
AI runtime
• Vercel AI SDK + OpenAI (gpt-5.4-nano classify, gpt-5.4 reason, text-embedding-3-small embeddings).
• Tool/MCP registry with ToolGateway 10-step pipeline (auth · permission · taint · rate · budget · args-validate · execute · sanitize · log · trace).
Block 9 — QA Approach
Test pyramid (target mix)
UAT 2% System / E2E 8% Integration 20% Unit 70%
Test Type Ownership
Test Type | Scope | Owner | Tooling
Unit | Function / class / handler / component | Dev | Vitest · Testing Library · co-located tests (no tests/ dirs)
Integration | Module API · cross-handler flows · tRPC contract | Dev + QA | Vitest + real Postgres (testcontainers)
System / E2E | End-to-end user flow | QA | Playwright · critical flows only
Performance | Load / stress on hot endpoints | QA + SRE | k6 · run pre-M04
Security | SAST · DAST · dependency audit · prompt-injection suite · penetration test | Security (+ AI Eng for AI boundary) | CodeQL · Snyk · custom adversarial suite · bun audit
UAT / Pilot rehearsal | Business scenario | BA + Pilot Team | Scripted rehearsal + real pilot users
Exit criteria (gate every milestone)
• 0 critical bugs
• ≤ 2 high bugs with documented workaround
• ≥ 95% test pass rate
• ≥ 70% coverage (lines, functions, branches) per CLAUDE.md
• Security scan clean (SAST + dependency audit)
• AI adversarial test suite green (Phase 2)
Discipline rules
• Test first. No test = feature not started. Test not passing = not done.
• Handlers: unit test every error path, not just the happy path.
• Cross-module: integration test against a real database.
• Critical user flows: Playwright E2E.
Block 10 — CI/CD Approach
6-step pipeline
• Source — GitHub · trunk-based with feature branches · PR review required · CI green + 1 approval to merge
• Build — GitHub Actions · Turborepo remote cache · lint · unit · SAST · image build (ARM64 only)
• Test — Vitest · Playwright · integration against real Postgres via testcontainers · coverage report attached to PR
• Package — Docker ARM64 image · ECR push · SBOM generation · Cosign sign
• Deploy — ECS Fargate rolling deploy to a single pilot-staging env (no production env in this MVP) · auto-rollback on health check failure. Production environment is a post-pilot scope item; the pilot itself runs on staging.
• Monitor — Langfuse · CloudWatch · Sentry · SLO dashboards · on-call rotation (pilot only)
DORA targets (Elite-level aim)
DORA metric | Target
Deploy frequency | Daily (at least during build phase)
Lead time for change | < 1 day from PR-open to staging-live
Change failure rate | < 15%
MTTR | < 1 hour
Block 11 — AI Approach — The Differentiator
AI is integrated into each role to accelerate delivery and reduce manual effort. Budgeted on 1× Claude Max x20 shared subscription + ~$200 AI API cap.
Role | AI Use | Impact Target
Dev | Code assistant · auto-completion · unit-test generation · architecture Q&A | ↑ Productivity 25–40%
QA | Auto-generated test cases · visual regression · adversarial prompt generation | ↓ Manual effort 50%
PM | Risk prediction · velocity forecast · early-warning retro synthesis | Early warning 2–3 sprints
BA | Requirement parsing · user-story refinement · legacy-system interview synthesis | Faster discovery 30%
Ops | Anomaly detection · incident triage · RCA assist | ↓ MTTR 40%
Client (in-product) | Agent + conversational AI (optional add-on to the product itself) | Business-value uplift measured in pilot outcomes G1–G7
Principle: Human-in-the-loop by default. Sample any AI-generated code in CR. No autonomous writes in user-facing paths without HITL approval.
Block 12 — Definition of Success
Four quadrants. Each quadrant is green for pre-pilot sign-off.
Delivery
• Go-live (pilot start) within ±1 week of plan (Wed 17 Jun 2026).
• Budget variance ≤ 10% of approved shape.
• 100% of MVP scope from 03-Scope Block 2 delivered or explicitly deferred via CR.
• 0 critical bugs at pre-pilot gate.
Quality
• ≥ 70% coverage per CLAUDE.md (lines, functions, branches).
• ≥ 95% pre-pilot rehearsal pass rate.
• Defect leakage to pilot < 5%.
• Security scan clean + penetration test returns zero permission-leak incidents.
Adoption
• Pilot active-user rate ≥ 80% in pilot W4 (measured: logged in ≥ 3 times in the week).
• Pilot CSAT ≥ 4 / 5 in W4 interviews.
• Training / onboarding completion ≥ 90% among pilot users.
• Support-ticket volume trending downward across pilot W1 → W4.
Outcome
• G1 chase-up reduction: meaningful reduction measured by time diary.
• G2 workaround displacement: < 1/3 of pilot users still keep side-records.
• G3 leadership behaviour change: ≥ 2 of 5 leaders answer yes concretely to all three interview questions.
• G4 AI capture recall ≥ 70%; reviewer acceptance ≥ 70%.
• G7 conversational AI first-attempt correctness ≥ 80%; zero permission-leak incidents.

## 06-Resources
Sheet: 06-Resources
PPTX Slide 17. Allocation + RACI matrix.
Block 1 — Allocation
Role | Person | Effort | Tracks covered
PM | Canh Ta | 50% | All tracks (delivery · backlog · prioritisation · scope · comms)
PM (co-owner) | Nguyen Hương Ly | TBD | Joint ownership; allocation set at Kickoff
PO + Sponsor | Hung Vu (dual-hatted) | BOD-level (weekly sync + sprint review) | Story acceptance at sprint review; Definition of Success sign-off; scope veto; kill-criteria evaluation; gate decisions
Scrum Master | TBD | 50% | Ceremonies, velocity, unblocking
BA | TBD | 50% (flexible) | Planner MVP requirements / UAT / pilot feedback + parallel legacy-systems discovery (EMS · Timesheet · Hiring · Resource Insight). PM covers capacity gaps.
AI Engineer | TBD | 100% | Core AI Agent (Phase 1 + Phase 2) + Planner-domain Agent integration (transcript sub-agent, conversational executor)
Full-Stack #1 | TBD | 100% | Both full-stack devs own their assigned modules/features end-to-end (BE + FE + Core-slice work for those features). Split between FS#1 and FS#2 is by module/feature, not by BE vs FE discipline — neither dev specialises in one layer. Per-feature ownership finalised at Kickoff (see 03-Scope Block 1 WBS Owner column for provisional assignment) and reflected in this allocation row.
Full-Stack #2 | TBD | 100% | See Full-Stack #1 — both devs full-stack. Per-feature ownership finalised at Kickoff; provisional split on 03-Scope Block 1.
Data Engineer | TBD | 100% (contingent on W1 onboarding) | Core Data Platform (deferred from MVP if onboarding slips; operational-DB queries carry aggregated views during pilot)
Designer-Lead (borrowed) | Mia / Darcy | Part-time, named windows | HITL review queue UX · aggregated dashboards UX · action detail view UX · design-system adherence reviews
Allocation % per track (indicative, for the bar chart)
Each Full-Stack dev is shown with a total 100% that is split across tracks; the same-row % for the two FS devs reflects the expected per-Kickoff split. Both are full-stack — these percentages are by module/feature scope, not by BE-vs-FE discipline.
Track | PM | PO | SM | BA | AI Eng | FS#1 | FS#2 | DE | Designer
Planner (module features, BE + FE) | 20% | 20% | 15% | 35% MVP share (flexible) | 40% (Agent integration) | 60% | 40% | 30% (if in) | 60%
Core Backend (horizontal) | 10% | 5% | 10% | 0% | 0% | 10% | 30% | 10% (if in) | 0%
Core Frontend (horizontal) | 10% | 5% | 10% | 0% | 0% | 20% | 20% | 0% | 40%
Core AI Agent (horizontal, Phase 1 + 2) | 10% | 5% | 15% | 0% | 60% | 10% | 10% | 0% | 0%
Governance + ceremonies | 50% | 65% | 50% | 0% | 0% | 0% | 0% | 0% | 0%
BA legacy-discovery (parallel) | 0% | 0% | 0% | 65% (flexible — inverse of Planner) | 0% | 0% | 0% | 60% (if in) | 0%
Rows add to ~100% per role across all tracks. FS#1 and FS#2 allocations are illustrative — the actual per-feature ownership is decided at Kickoff; both devs cover their share of Planner + Core work end-to-end. The Data Engineer row is shown twice (Planner aggregated views + legacy-discovery data feeding) because the likely allocation is split between Core Data Platform work and feeding legacy-system data into the future modules pipeline.
Block 2 — RACI Matrix
Rule: Every task row has exactly one Accountable. R = Responsible (does the work), A = Accountable (one person, owns the outcome), C = Consulted (provides input), I = Informed (kept in the loop).
Task | PM | PO | SM | BA | AI Eng | FS#1 | FS#2 | DE | Designer | Sponsor
Requirements definition | A | C | I | R | I | I | I | I | I | I
Architecture decisions | A | I | I | I | C | C | R | C | I | I
UX / design artefacts | A | C | I | C | I | C | I | I | R | I
Backlog prioritisation | A/R | C | I | C | C | C | C | I | I | I
Sprint planning | A | R | R | C | C | C | C | I | I | I
Story acceptance at sprint review | C | A/R | I | C | I | R | R | I | C | I
Planner module implementation (BE + FE — per-feature ownership set at Kickoff) | I | I | I | I | I | A/R\* | R | I | C | I
Core Backend (horizontal) implementation | I | I | I | I | I | R | A/R\* | C | I | I
Core Frontend (horizontal) implementation | I | I | I | I | I | A/R\* | R | I | C | I
Core AI Agent implementation (Phase 1 + 2) | I | I | I | I | A/R | C | C | I | I | I
Planner Agent integration (transcript, HITL, conversational) | I | I | I | I | A/R | C | R | I | I | I
Testing (unit + integration) | bar: I to I
Testing (system / E2E) | C | I | I | C | R | R | R | R | I | I
Adversarial / penetration testing (AI boundary) | C | I | I | C | A/R | I | R | I | I | I
Release / deployment | A | I | I | I | R | R | R | I | I | I
Pilot measurement + interviews | C | I | I | A/R | C | I | I | I | I | I
Scope change approval (CR) | A/R | C | C | C | C | C | C | I | I | C
Scope veto | A/R | I | I | I | I | I | I | I | I | C
Kill-criteria evaluation | C | I | I | R | C | I | I | I | I | A
Wave rollout decision | R | I | I | I | I | I | I | I | I | A
Pilot-to-Wave gate decision | R | I | I | C | I | I | I | I | I | A
Project closure | R | I | I | C | I | I | I | I | I | A
Read: PM is Accountable for delivery and backlog; PO (Hung Vu, dual-hatted) is Accountable for story acceptance; Sponsor (also Hung Vu) is Accountable for gate decisions and closure. Every other row has exactly one A.
\ On the Planner / Core BE / Core FE rows, A/R indicates the feature owner (either FS#1 or FS#2) for a given feature; the R next to it is the partner dev who contributes. Per-feature ownership is set at Kickoff and recorded in the Owner column of 03-Scope Block 1 WBS-Master. Each full-stack dev owns their assigned features end-to-end — both BE and FE layers of those features.

## 07-DCA
Sheet: 07-DCA
PPTX Slide 24. Dependencies · Constraints · Assumptions.
Block 1 — Dependencies
External and cross-track dependencies that must be resolved for the plan to execute on schedule.
ID | Description | Impact if late | Owner | Due Date
D-01 | Microsoft 365 tenant admin consent for Entra ID SSO application registration | Blocks Core BE W-B03 and every subsequent sign-in | IT (SETA) | Fri 24 Apr 2026 (W1)
D-02 | Microsoft Graph application permissions granted: User.Read.All, Group.Read.All, ChatMessage.Read.All (or tenant-filtered equivalents), Tasks.ReadWrite, OnlineMeetings.Read.All, CallRecords.Read.All, transcript webhook scope | Blocks Core BE W-B14 and Planner W-P11 | IT (SETA) | Fri 01 May 2026 (W2)
D-03 | AWS account + VPC + ECS cluster + ECR + Secrets Manager + CloudFront distribution provisioned (Terraform ready) | Blocks all deployments | IT (SETA) | Fri 01 May 2026 (W2)
D-04 | OpenAI API key provisioned, budget guardrails set on OpenAI side | Blocks Core AI W-A01 and every AI-driven feature | PM | Fri 24 Apr 2026 (W1)
D-05 | Langfuse deployment target confirmed (self-hosted ECS vs managed cloud) | Blocks Core AI W-A08 | CTO | Fri 24 Apr 2026 (W1)
D-06 | Designer-Lead (Mia / Darcy) weekly window confirmed in writing, per critical-surface schedule | Designer-critical surfaces (HITL queue, dashboards, action detail) slip | CEO + Designer's primary project lead | Tue 22 Apr 2026 (Kickoff)
D-07 | Data Engineer onboarding decision (will DE join in W1?) | If no, Core Data Platform is deferred per BMM; aggregated views fall back to direct operational-DB queries in pilot | CTO | Tue 22 Apr 2026 (Kickoff)
D-08 | Pilot team nomination and pilot-rehearsal schedule | Blocks M04 pre-pilot gate and pilot start | PMO + PM | Fri 29 May 2026 (W6)
D-09 | Vietnamese government holiday-announcement dates confirmed by SETA HR | Affects Sprint 1 capacity accuracy on 04-Timeline Block 5 | HR | Tue 22 Apr 2026 (Kickoff)
D-10 | SBOM + software-composition-analysis tooling integrated into CI | Blocks 02-Contract Block 3 item #3 | DevOps | Fri 15 May 2026 (W4)
D-11 | Admin scope configuration signed off for pilot (which teams / projects ingested) | Blocks pilot start | Admin (role assignment) + PM | Fri 12 Jun 2026 (W8)
D-12 | Existing email (SES) from-address + DNS records provisioned | Blocks notifications + reminders + digest | IT | Fri 08 May 2026 (W2-W3 boundary)
Block 2 — Constraints
Type | Description | Impact
Time | MVP pilot-ready by end W8 (Tue 16 Jun 2026); pilot-to-Wave gate W12. Hard stop on build at W8. | Scope must fit capacity — see 03-Scope Block 1 rollup vs capacity note.
Capacity | ~5.5 FTE team: 3 FTE builders (2 FS + 1 AI Eng) + 50% each of PM, SM, BA + borrowed Designer-Lead. DE contingent on onboarding. | ~3.1× over on planned midpoint — scope trade-offs required (see 03-Scope Block 1 Recommendation).
Budget | Team time only. Plus 1× Claude Max x20 shared subscription (PM-held) and ~$200 AI API cap. Infrastructure + MS 365 licences under existing organisational accounts. | No external dollar budget to draw from; all tradeoffs are in time + scope, not money.
Language | English only for UI, email, AI outputs, and pilot measurement instruments. | VN-speaking users are assumed to read English in product; no translation layer.
Client | Current desktop browsers (Chromium · Firefox · Safari latest); responsive where feasible; mobile-native deferred. | Pilot users on mobile get responsive web, not a native app.
Stack | Next.js multi-zones · NestJS modular monolith · Drizzle + Postgres 16 · tRPC · ECS Fargate ARM64. No deviations. | ARM64 dependency check required for every added package.
Region | AWS ap-southeast-1 (Singapore) exclusively for compute + data. | Cross-region breakout is a process change, not a plan item.
Environments | Single pilot-staging environment in this MVP. No production environment. Pilot runs on staging. Production environment is scoped post-pilot (pre-Wave-1). | Release runbook, rollback drills, monitoring, on-call rotation all target staging. Production-grade hardening (scaling, DR, backup windows, blue-green) is deferred to the post-pilot scope.
Integration | Microsoft 365 tenant (Teams transcripts · Planner · Entra ID directory) is the single upstream integration. No other third-party. | Teams-only capture; hallway / phone / external meetings are out of scope.
Retention | Action data, evidence, transcripts, audit indefinite by default; admin can delete with logged reason. | Storage cost rises over time; retention policy revisited post-pilot.
Team rotation | Team core must not be rotated in the 2-month build window. | If rotated, ramp-up cost + rework risk is R-Team in 08-Risks-Issues.
Block 3 — Assumptions
Assumption | Impact if false
Microsoft Teams is SETA's dominant meeting channel and transcription is actively enabled tenant-wide. | Capture volume drops; Agent training signal weakens; G4 recall target at risk.
Meetings captured by the Agent are calendar-backed scheduled meetings; ad-hoc Teams meetings created via API are not expected in scope. | Some meetings fall outside capture; users may assume coverage they don't have.
Admin configures auto-capture scope conservatively at pilot launch (opt-in by team). | Privacy pushback; pilot users feel surveilled; workaround displacement worsens.
Internal engineering capacity covers the seven-person team plus the Designer-Lead for the full 2-month build window. | R-Capacity realised; scope rebaseline via CR.
Designer-Lead retains the agreed weekly window for HITL queue, dashboards, and action detail surfaces. | Design quality on the three critical surfaces slips; R-Designer realised.
AI productivity assumption: ~2× on appropriate tasks (code generation, test generation, docs); potentially negative on critical-path design. | Velocity below plan; scope rebaseline via CR.
Data Engineer onboarding is decided at Kickoff. | If DE not onboarded, Core Data Platform is deferred and aggregated views run on direct operational-DB queries; revisited before Wave 2.
Pilot users engage with measurement (time diary, interviews, query review). | Outcome measures (G1–G7) become unreliable; pilot gate decision is weakened.
Microsoft Graph API rate limits and subscription-renewal cadence are predictable within documented bounds. | R-MS-Graph realised; polling intervals widened; sync latency degrades.
OpenAI API availability and cost stay within the approved budget shape (~$200 cap). | Cost-meter circuit breaker triggers; conversational AI disabled per kill switch until budget increased.
Penetration-style adversarial testing by PM + BA is sufficient proof for pre-pilot security sign-off (no external audit in the 2-month window). | If not sufficient, external pentest is a post-pilot blocker for Wave 1.

## 08-Risks-Issues
Sheet: 08-Risks-Issues
PPTX Slides 25-26. Risk register · Heat map · Issues log · Process.
Block 1 — Risk Register
Probability (P) and Impact (I) scored as L / M / H. Score = worst of P×I (L, M, H, H+). Status updated weekly.
ID | Risk | P | I | Score | Mitigation | Owner | Status
R-01 | Scope accumulation. PM at 50% with shared coordination duties; without explicit scope authority, features accumulate mid-build. | H | H | H+ | PM given written veto authority by Sponsor at Kickoff. Bi-weekly scope check in retros. Every addition requires an explicit cut. Scope-change discipline on 03-Scope Block 4. | PM | Open
R-02 | Designer-Lead availability slip. Designer (Mia/Darcy) is borrowed from another project; demands may compete with their primary project. | H | H | H+ | Time commitment agreed in writing with named weekly windows per critical surface (HITL queue · aggregated dashboards · action detail). PM escalates to Sponsor if availability slips. | PM + Sponsor | Open
R-03 | Capacity over-commit. Midpoint WBS estimate (~348 MD) exceeds builder capacity (~114 MD over 8 weeks net of VN holidays) by ~3.1×. | H | H | H+ | At Kickoff: pick scope-trade path per 03-Scope Block 1 Recommendation (defer Admin console · compress aggregated views · scope conversational AI to pre-built queries · lean on DE if onboarded). Rebaseline via CR. | PM | Open
R-04 | DE onboarding delay. Core Data Platform is on the critical path for optimal aggregated views and the executive digest. | M | M | M | If DE not onboarded by W1, Core DP is deferred; aggregated views and digest run on direct operational-DB queries in pilot. Architecture revisited before Wave 2. | CTO | Open
R-05 | AI proposal quality (hallucination · wrong owner · wrong deadline). | M | M | M | Pilot informs prompt tuning. Per-capability kill switch. Rejection rate tracked in Langfuse. Confidence threshold tuned during pilot. | AI Eng | Open
R-06 | Single-person dependency on AI Engineer. Owns Core AI Agent Phase 1 + 2, Planner-domain sub-agent, extraction prompts, conversational executor. | M | M | M | Cross-team knowledge sharing W1. Architecture decisions captured in 02-Contract Block 1 and on each sprint's review. Conversational AI scope kept tightly read-only (REQ-22 per BRD §4.3). | AI Eng + PM | Open
R-07 | Permission-leak via conversational AI. A query returns data the user should not have access to due to a gap in how AI translates natural language into the permissions engine. | M | H | H+ | Every conversational query passes through the same permissions engine as UI queries (NFR-04). AI generates structured queries permission-checked before execution. Penetration-style testing in pre-pilot W8 with deliberately adversarial queries. Zero permission-leak incidents required for M04 sign-off. | AI Eng + QA | Open
R-08 | Meeting organiser flooded with disambiguation requests. Heavy meeting organisers (PMs · CEO in strategy meetings) accumulate many unassigned-owner proposals. | M | M | M | Confidence threshold tuned during pilot to set the right precision/recall balance. Disambiguation proposals batched into a single daily email per organiser. 7-day auto-expiry with Admin fallback. Bulk-reject in queue UI. | AI Eng | Open
R-09 | Microsoft Planner polling architecture. Graph does not provide change notifications for Planner tasks; aggressive polling across many plans risks throttling. Conservative polling extends sync latency. | M | M | M | Polling interval Admin-configurable. Start at 5-minute intervals for pilot; monitor rate-limit headers and tune. Scope narrowed to Admin-designated plans. Delta queries used where available. | FS#2 | Open
R-10 | Microsoft Graph tenant admin consent delay. Required for Entra ID SSO, directory sync, Teams transcript subscription, Planner CRUD. | M | H | M | Raised at Kickoff with IT. Fallback: ship identity + permission primitives behind magic-link in W1 so development is not blocked; wire SSO when consent lands. | IT + PM | Open
R-11 | OpenAI cost runaway. Free-form queries + Phase 2 router fan-out to multiple sub-agents; unbounded token spend if router misclassifies. | M | M | M | Circuit breaker at the cost layer (per-user + per-tenant daily budget). Budget dashboard visible to Admin. Hard cap on concurrent sub-agent spawn. Kill switch disables conversational AI independently. | AI Eng + Admin | Open
R-12 | Transcript subscription latency / reliability. Graph change-notification delivery variance; subscription renewal can miss; transcripts may arrive minutes to hours after the meeting ends. | M | M | M | Subscription-renewal job runs ahead of expiry with alerting. Fallback reconciliation job polls callRecords endpoint for missed transcripts. Planner UI surfaces "transcript pending" state transparently. | FS#2 + AI Eng | Open
R-13 | VN holiday capacity hit in Sprint 1. Effective 7 working days instead of 10 in S1 shifts M01 risk rightward. | H | M | M | Calendar-captured on 04-Timeline Block 5. Sprint 1 scope trimmed to foundations-only; feature build starts S2. PM monitors burn-down; rebaseline via CR if M01 slips. | PM | Open
R-14 | Team rotation during the build. Core team members pulled onto other projects; ramp-up cost + rework. | M | H | M | Written commitment from Sponsor at Kickoff that core team is not rotated for the 8-week build. Pairing + documentation on every architectural decision reduces bus-factor. | Sponsor + PM | Open
R-15 | Pilot measurement incomplete. BA at 50% with parallel legacy-discovery workstream; pilot interviews + ground-truth extraction may starve. | M | M | M | Ground-truth sample reduced from ~20 to ~12 meetings to fit BA capacity. Pilot Team Lead co-conducts IC interviews (peer rapport). PM covers BA capacity gaps. Allocation flexibility confirmed at Kickoff. | BA + PM | Open
R-16 | Penetration test insufficient. PM + BA adversarial testing pre-pilot may miss deeper security flaws that an external pentest would catch. | M | H | M | Defence-in-depth at every layer (RLS · canDo · tRPC middleware · AI boundary). External pentest scheduled post-pilot before Wave 1. Document scope of PM/BA pre-pilot test on this workbook. | PM + Sponsor | Open
R-17 | Launch communication backfires (managers use aggregated views punitively rather than coachingly). | M | M | M | Launch comms pack (W-PM05) coaches on coaching-first framing. Pilot Week-1 interview asks managers what they did with team-health view; course-correct if needed. | PM + BA | Open
Block 2 — Risk Heat Map
Place risk IDs in cells. Colour the cell fill matching 04-Timeline Block 4 status legend (H+ = red, H = red, M = yellow, L = green).
| Impact L | Impact M | Impact H
P H | — | R-13 | R-01, R-02, R-03
P M | — | R-04, R-05, R-06, R-08, R-09, R-11, R-12, R-15, R-17 | R-07, R-10, R-14, R-16
P L | — | — | —
Block 3 — Issues Log
Defects, blockers, and operational issues picked up during the build and pilot. Empty at Kickoff; populated throughout.
Issue ID | Description | Severity | Owner | Status | ETA
ISS-000 | Template row — delete when first real issue lands | — | — | — | —
Severity definitions
Severity | Meaning | SLA (from 05-Approach Block 3)
P1 — Critical | Pilot-impacting, security, data loss | 15 min response · 4 h resolve
P2 — High | Blocks pilot feature or gate | 1 h response · 1 bd resolve
P3 — Medium | Degraded behaviour, workaround available | 4 h response · 3 bd resolve
P4 — Low | Cosmetic, nice-to-have | 1 bd response · next release
Block 4 — Risk & Issue Management Process
Four steps, run weekly at the BOD sync and daily at stand-up.
• Identify. Capture from team, stakeholder, retrospective, pilot user, or customer. Every new risk / issue gets an ID on this sheet.
• Assess. Probability × Impact → scoring → prioritise. Sort this sheet by score descending at every BOD weekly sync.
• Mitigate. Action plan with owner, due date, and — if needed — budget ask. Record the mitigation in this sheet's Mitigation column.
• Monitor. Weekly review at BOD sync; mark as closed when resolved. No silent closure — status change is a row update.
Cadence
• Daily stand-up: SM runs through open issues sorted by severity.
• Weekly BOD sync: PM walks through open risks + top issues; decisions recorded in the sheet.
• Sprint retrospective: SM prompts "any new risks to surface?"; filed before next sprint.
• Monthly Steering Committee: PM presents risk heat map and top mitigations.

## 09-ExecSupport
Sheet: 09-ExecSupport
PPTX Slide 27+. Budget · Decision SLA · Kill criteria.
Block 1 — Budget
The approved budget shape, not a dollar figure.
Resources approved
Category | Scope | Note
Team time | 2× Full-Stack Dev (100%) · 1× AI Engineer (100%) · 1× Data Engineer (100%, contingent) · 50% each of PM, Scrum Master, Business Analyst · borrowed Designer-Lead (part-time, named windows) | 8-week build + 4-week pilot + phased rollout TBD
AI assistance (build) | 1× Claude Max x20 shared subscription | Used for code generation, test generation, design drafting, documentation, prompt development
AI API runtime | ~$200 cap on OpenAI API usage | For Agent extraction, confidence scoring, conversational queries. Circuit-breaker in Core AI W-A13 enforces
Infrastructure | AWS (ap-southeast-1), ECS Fargate ARM64, ECR, Secrets Manager, RDS, S3, CloudFront, WAF, ALB | Under existing SETA organisational AWS account
Microsoft 365 licences | Existing SETA tenant — no additional licences | Entra ID + Teams + Planner coverage already present
Observability | Langfuse (self-hosted ECS) · CloudWatch · Sentry | Self-hosted to avoid per-trace cost
Buffer | 10-15% time buffer already absorbed into effort ranges on 03-Scope Block 1 | No monetary buffer line; scope is the buffer
Excluded from budget
• No external professional services (e.g., Microsoft consulting, external QA firm).
• No external penetration test during the 2-month build (scheduled post-pilot pre-Wave-1 as a separate budget ask).
• No commercial product licences (e.g., Datadog, Figma upgrade, CI usage beyond GitHub Actions baseline).
• No dedicated customer-success or training contractor; pilot coaching runs on internal time.
Budget tracking cadence
Weekly BOD sync reviews:
• OpenAI API spend vs cap (circuit-breaker state).
• Builder days consumed vs planned (from 04-Timeline Block 3).
• Any CR-driven budget change requests (routed via 03-Scope Block 4 process).
Block 2 — Decision SLA
Time targets for getting decisions back to builders. Missing these SLAs means work blocks.
Decision type | Approver | Response SLA | Escalation
Sprint scope / backlog prioritisation | PM | 24 hours | Sponsor if PM unavailable
Story acceptance at sprint review | PO (Hung Vu, dual-hatted) | At sprint review + 24 h grace for async follow-up | PM to chase; escalate to Sponsor if 48 h
Architectural change on Core slice | Tech Lead (FS#2) with CTO approval | CTO within 24 hours on Core architecture questions | PM escalates to Sponsor at 48 h
Scope change (CR) | PM (under veto authority); CCB (Sponsor + CTO + PMO) for material change | PM 48 hours for small CR; CCB 5 business days for material | PM escalates to Sponsor; CCB is scheduled ad-hoc
Budget variance | Sponsor | 48 hours | —
Kill-criteria threshold triggered | Steering Committee | 1 week to convene and decide | —
Pilot-to-Wave gate decision | Steering Committee (M06) | W12 | —
Wave rollout go / no-go | Sponsor + PMO | 48 hours per wave | —
Post-incident review | PM + Tech Lead | Within 1 week of incident closure | —
Block 3 — Kill Criteria
Thresholds that, if crossed, trigger a mandatory re-evaluation. Evaluated at the Pilot-to-Wave gate (M06) and during the pilot. Require Steering Committee endorsement before the pilot begins.
Measure | Pause-and-tune threshold | Stop-and-reconsider threshold
AI capture recall (G4) | < 60% — 4 weeks of prompt tuning before continuing | < 40% — fundamentally reconsider the Agent approach
Workaround displacement (G2) | 50% of pilot users still keep side-records | ≥ 75% — product is parallel, not primary — rework UX
Chase-up reduction (G1) | < 20% vs baseline | 0% or negative — core value proposition not landing
Leadership behaviour change (G3) | 0 of 5 leaders answered yes to all three questions | Same threshold — 0 of 5
Conversational AI correctness (G7) | < 70% first-attempt correctness | Any permission-leak incident is an immediate stop (no pause-and-tune)
HITL acceptance rate (G6) | < 50% acceptance | < 30% — proposal quality is not salvageable in the near term
Team health / burnout signal | Any team member reports overload in retro | Two or more team members signal overload
Budget overrun | AI API spend > 150% of $200 cap | AI API spend > 250% of cap without justified scope expansion
Process on trigger
• PM flags the triggered threshold in the weekly BOD sync.
• Steering Committee convenes within 1 week; decides: Proceed · Pause-and-tune · Pivot · Stop.
• Decision recorded on this sheet with date + reason.
• If Stop or Pivot: close-out plan authored by PM, reviewed by CTO; communications by PM; archival of work products.
Stage acceptance (rollup)
Stage | Criterion
Build complete (M04) | All 03-Scope Block 2 scope delivered or explicitly deferred via CR; 05-Approach Block 9 QA exit criteria met; pilot team onboarded; measurement instruments ready
Pilot-to-Wave gate (M06) | Five outcome measures (G1–G7) reviewed against Kill Criteria above; Committee decision: proceed / pause-and-tune / pivot
Wave-to-wave gate | IT and PMO confirm no blocking issues; outcome measurements repeated lightly on the new wave; adoption drop-off monitored
Project closure (M09) | Full coverage + 4 weeks stable operation; Steering Committee review; next Future module scoped per SETA priority

## Track-Planner
Sheet: Track-Planner
Vertical track. User-facing Planner module. Integrates Core BE + Core FE + Core AI Agent horizontal slices into a product.
Block 1 — Purpose
Deliver the Planner MVP: action tracking, evidence capture, Meetings page, HITL review queue, aggregated views, executive digest, Microsoft Planner bidirectional sync, conversational AI interface, and admin console — the user-facing product that proves Future's agent-native module pattern works and gives SETA's ~400 staff a single place to track commitments.
Planner is the only user-facing track in this MVP. Everything the pilot users touch is on this track; the three Core tracks are foundations underneath it.
Block 2 — Scope
2.1 In scope
Everything listed on 03-Scope Block 1 WBS rows prefixed W-P. Feature summary:
• Action domain + CRUD + lifecycle + priority + stakes + project tag + deadline + owner + delegator (unified across manual / AI-proposed / MS-Planner-synced sources).
• Evidence, attachments, comments, checklists.
• Plan / project CRUD, membership, labels, buckets.
• Action views: Board · Grid · Schedule · Charts.
• Personal Hubs: My Plans · My Tasks · My Day (with carry-over).
• Meetings page: list + transcript viewer + linked actions + on-demand "Extract actions with AI".
• HITL review queue: proposals list + detail + accept / edit-and-accept / reject + unassigned-owner routing + bulk-reject.
• Planner-domain Agent sub-agent for transcript extraction (consumes Core AI runner).
• Aggregated views: Team health · Manager drill-down · Account Manager · PMO portfolio · Admin system health.
• Executive weekly digest email.
• Microsoft Planner bidirectional sync: OAuth + discovery + push + pull + conflict resolution (title · status · deadline).
• Admin console: scope config · role assignment · kill switches · rate limits · anomaly thresholds · proposal expiry · backlog view · audit-log view.
• Conversational AI query UI (read-only, session-scoped, permission-enforced; backed by Core AI router + Planner executor).
• Notifications: email + in-app for lifecycle + deterministic 3-day / 1-day / overdue reminders.
• Escalation engine (AI-drafted, HITL-approved) and anomaly-auto-pause.
2.2 Out of scope
Inherit 03-Scope Block 3 plus these Planner-specific carve-outs:
• No write operations via conversational AI for this release.
• No custom chart builder or user-selected metrics. Pre-built chart set only.
• No in-product coaching / onboarding tours (launch comms pack covers this out-of-band).
• No import from legacy action-tracking tools (users start fresh).
• No cross-tenant collaboration.
• No AI-drafted evidence text (evidence note is manual per BRD REQ-05).
2.3 Dependencies
• Core Backend track: identity · permissions · audit · RLS · outbox · MS Graph adapter · email gateway — needed by S1–S2.
• Core Frontend track: @future/ui · @future/app-layout · design tokens · theme toggle · notifications popover · SSE client — needed by S1–S2.
• Core AI Agent track Phase 1: LLM client · prompt store · confidence scoring · HITL routing engine · tool registry + ToolGateway · SSE — needed by S2.
• Core AI Agent track Phase 2: prompt-injection defence · permission at AI boundary · free-form router · cost meter — needed by S4.
• External: Microsoft 365 tenant admin consent (D-01 · D-02 on 07-DCA).
• Designer-Lead weekly window for HITL queue, aggregated dashboards, action detail.
Block 3 — Deliverables & Acceptance
High-level deliverables rolling up WBS rows. Each ties to at least one milestone.
# | Deliverable | Acceptance | Evidence | Milestone
D-P01 | Action core (domain · CRUD · lifecycle · evidence · comments) | Users can create · edit · complete actions with evidence and comments end-to-end | Playwright e2e + unit coverage ≥ 70% | M03
D-P02 | Plans + Views | Board / Grid / Schedule / Charts views render for personal + plan scope with filter + group-by | Visual QA + Playwright | M03
D-P03 | Personal Hubs + Dashboard | My Day / My Plans / My Tasks with carry-over; dashboard counts match filters | UI tests + dashboard snapshot test | M03
D-P04 | Meetings page + on-demand extraction | Meeting list + transcript view + linked actions + rate-limited extraction triggering HITL proposal | Integration + e2e; rate-limit enforced | M03
D-P05 | HITL review queue | Queue flow round-trips to Agent; routing + expiry + backlog alerts working | Integration + agent trace review | M03
D-P06 | Agent integration (transcript sub-agent + prompts + confidence wiring) | Transcript → proposal end-to-end with confidence-scored output | Langfuse trace visible; proposal schema validated | M03
D-P07 | Aggregated views (Team + Manager + PMO + Account Mgr + Line Mgr) | Drill-down respects reporting chain; no cross-hierarchy bypass; charts from live data | UI + permission tests | M04
D-P08 | Executive weekly digest | Phone-first email renders; dry-run passes | Email render proof on real client | M04
D-P09 | Microsoft Planner bidirectional sync | Round-trip ≤ 5 min on title/status/deadline; deletion marks Cancelled | Integration tests against test tenant | M04
D-P10 | Admin console | Scope config + kill switches + rate limits + backlog view + audit log | UI + backend config tests | M03 (phase 1) / M04 (phase 2)
D-P11 | Conversational AI interface | Query preview before execute; permission enforced; 30-query eval ≥ 80% | Eval suite green | M04
D-P12 | Notifications + Reminders | Per-event email + in-app; deterministic reminders firing | Worker logs + user mailbox proof | M03
D-P13 | Escalation engine + anomaly detection | AI-drafted escalation reviewed + sent; anomaly threshold auto-pauses | Integration tests | M04
D-P14 | Data retention + admin deletion | Admin delete with reason; logged to audit | Audit-log query proof | M04
Block 4 — WBS (task-level)
Full task-level WBS lives on 03-Scope Block 1 rows W-P01 .. W-P30. Top 5 tasks by effort on this track:
Rank | ID | Feature | Effort High (MD) | Confidence | Owner
1 | W-P19 | Microsoft Planner bidirectional sync | 14 | L | FS#2
2 | W-P07 | Views (Board · Grid · Schedule · Charts) | 10 | H | FS#1
3 | W-P20 | Team + Manager aggregated views | 10 | M | FS#1
4 | W-P23 | Admin Console — scope + role + kill | 10 | M | FS#1
5 | W-P26 | Planner query executor (conversational) | 9 | L | AI Eng
Track totals (indicative, from WBS rollup): ~113–191 MD across 30 rows.
Block 5 — Sprint Plan (Planner-specific)
Overlays the master sprint plan on 04-Timeline Block 3.
Sprint | Planner goal | Exit criterion
S1 (W1–W2, 7 working days) | Action domain + CRUD + basic UI on top of Core foundations | Users can create / edit / complete / delete an action in staging via real SSO
S2 (W3–W4) | Views + Personal Hubs + Meetings page + HITL queue + transcript sub-agent + admin scope config | First Working Version demoable; HITL proposals round-trip through the queue
S3 (W5–W6) | Team + Manager + PMO aggregated views; MS Planner sync (OAuth + discovery + push); escalation engine; anomaly detection | Aggregated views live for pilot roles; push-to-Planner round-trips
S4 (W7–W8) | Conversational AI UI + executor; executive digest; pilot measurement instruments; polish + integration | All D-P* deliverables green; pre-pilot gate (M04) passes
Block 6 — Track-specific Risks
Track-only risks; cross-track risks live on 08-Risks-Issues.
ID | Risk | P | I | Mitigation | Owner | Status
RP-01 | MS Planner sync conflict resolution gets too complex under concurrent edits | M | H | Start with last-write-wins on a narrow field set (title / status / deadline) per scope in W-P19; document edge cases; defer richer conflict logic to post-MVP CR | FS#2 | Open
RP-02 | HITL queue grows too fast; meeting organisers overwhelmed | M | M | Daily digest batching; 7-day auto-expiry with Admin fallback; bulk-reject in UI. Also risk R-08 on 08-Risks-Issues. | AI Eng + FS#1 | Open
RP-03 | Aggregated views performance degrades under real data volume | M | M | Charts use daily snapshot tables (not live aggregation) from S3; query budgets per view; add indexes pre-pilot | FS#1 | Open
RP-04 | Conversational AI permission-leak path | M | H | Every query passes through the same permissions engine; penetration-style test pre-pilot (see R-07) | AI Eng | Open
RP-05 | Designer-Lead HITL queue + aggregated dashboard windows slip | M | M | Time windows named at Kickoff; PM escalates if slip (see R-02) | PM | Open
Block 7 — Definition of Done (track-level)
The Planner track ships when:
• All D-P01 .. D-P14 deliverables accepted on this sheet.
• Coverage ≥ 70% on all Planner modules.
• E2E Playwright suite green for critical flows (sign-in · create action · complete with evidence · HITL review · MS Planner sync round-trip · conversational query).
• Penetration test on conversational AI returns zero permission-leak incidents.
• Pilot measurement instruments (W-BA03) ready and reviewed with PM.
• MS Planner test-tenant sync round-trips within 5-minute latency.
• Exec digest dry-run reviewed by Sponsor.
• Admin console signed off by Admin role-holders.
Block 8 — Open Questions
Close by end of Kickoff week (W1).
Question | Owner | Needed by
Which pilot team? (target: 1 SETA dept + 1 project, ~20-30 users) | PMO + PM | Fri 29 May (W6)
MS Planner sync: which plans are Admin-designated for pilot? | Admin + PM | W5
Conversational AI: start with pre-built query cards (safe set) or direct NL from W8? | AI Eng + PM | W4
Unassigned-owner confidence threshold initial value | AI Eng + BA | W5
Executive digest recipient list + time-of-day preference | Sponsor + PMO | W6
HITL review-window default (BRD suggests 7 days; pilot may shorten) | PM + BA | W3
Admin role-holders for pilot (who gets kill-switch access?) | Sponsor + PM | W2
Notifications: opt-out granularity (all / per-event type / per-project?) | BA + FS#1 | W2

## Track-CoreBackend
Sheet: Track-CoreBackend
Horizontal track. Monorepo scaffolding, shared auth primitives, org-chart permissions engine, audit, RLS + tenant isolation, outbox + relay, MS Graph adapter scaffolding, outbound email, rate limiter + kill switches, observability, shared BE commons. No Planner-specific business logic lives here.
Block 1 — Purpose
Deliver the foundational backend slice that every Future module will reuse. Enough to unblock Planner's server-side work and to prove the patterns for subsequent modules (People · Time · Hiring · Projects · Performance · Finance · Goals · Insights).
Block 2 — Scope
2.1 In scope
03-Scope Block 1 WBS rows W-B01 .. W-B21:
• Monorepo scaffolding (Turborepo · Bun workspaces · shared tsconfig / eslint / prettier / lefthook / workspace template).
• Hexagonal + DDD module generator per project convention.
• Entra ID SSO primitive (OAuth flow · session · refresh · logout · tenant metadata).
• Magic link auth primitive (token mint · email delivery · validation · single-use).
• Org-chart permissions engine (rolegrant · rolepermission · delegation · canDo()).
• tRPC permission middleware + P2 visibility helpers + cross-hierarchy audit hook.
• Audit log primitive (schema + KernelAuditFacade + insert-only).
• RLS + tenant middleware with pool-client-per-request.
• Outbox event + polling relay + pg-boss harness.
• Rate limiter primitive + per-capability kill-switch primitive.
• Outbound email gateway (SES + SMTP · template registry · unsubscribe token).
• MS Graph adapter scaffolding (client wrapper · retry · rate-limit-aware batching · delta-query helper · subscription-renewal scheduler).
• Observability (OTel + Langfuse bridge · CloudWatch · structured logs · request-id propagation).
• Shared BE commons (error types · serializers · ID generators · clock abstraction · zod helpers · request-scoped context).
2.2 Out of scope
• Any module-specific business logic (Planner · People · Time etc.) — lives in those modules' tracks.
• User-facing features — none exist on this track.
• UI — Core Frontend owns.
• AI-specific primitives — Core AI Agent owns (LLM client · prompt store · confidence · HITL engine · tool registry).
• Data Platform (Glue · Iceberg · Athena · Cube) — that is a separate Core Data Platform track, contingent on DE onboarding.
2.3 Dependencies
• AWS account + VPC + ECS + ECR + Secrets Manager + RDS provisioning (D-03 on 07-DCA).
• Microsoft 365 tenant admin consent for Entra ID + Graph scopes (D-01, D-02).
• SES sending domain + DNS (D-12).
Block 3 — Deliverables & Acceptance
# | Deliverable | Acceptance | Evidence | Milestone
D-B01 | Monorepo + module template | turbo build green from clean clone; new workspace via turbo gen; pre-commit runs lint + format + type-check + tests | CI log | M01
D-B02 | Entra ID SSO + magic link | Sign-in round-trip against real tenant; magic-link TTL enforced; session cookie httpOnly + SameSite | Integration tests | M01
D-B03 | Org-chart permissions engine + middleware | canDo() correct across direct / delegated / cross-hierarchy matrix; P2 visibility enforced in list endpoints | Unit + integration tests | M01 / M03
D-B04 | Audit log | Insert-only; every logged operation appears; queryable by actor / subject / operation | Query proof on staging | M01
D-B05 | RLS + tenant middleware | Cross-tenant query denied at DB layer; lint rule blocks Promise.all on DB in handlers | Automated test | M01
D-B06 | Outbox + relay + jobs | Events published transactionally; relay delivers at-least-once; DLQ visible; scheduled jobs survive leader change | Integration tests | M01
D-B07 | MS Graph adapter scaffolding | 429 backoff respected; subscription renewal ahead of expiry; delta queries batch | Integration tests against test tenant | M01 / M02
D-B08 | Outbound email gateway | Template-driven emails send; bounce captured; unsubscribe respected | Sent + received email proof | M01
D-B09 | Rate limiter + kill switches | 429 at threshold; kill switch disables route atomically with audit | Integration tests | M02
D-B10 | Observability | Every tRPC call appears as span; trace IDs propagate worker boundaries | Langfuse + CloudWatch trace proof | M01
D-B11 | Shared BE commons | Utilities unit-tested; clock injected in time-sensitive handlers | Unit tests + usage in Planner handlers | M01
Block 4 — WBS (task-level)
Full WBS on 03-Scope Block 1 rows W-B01 .. W-B21. Top 5 by effort:
Rank | ID | Feature | Effort High (MD) | Confidence | Owner
1 | W-B05 | Org-chart permissions engine | 8 | M | FS#2
2 | W-B14 | MS Graph adapter scaffolding | 6 | M | FS#2
3 | W-B09 | Outbox + polling relay | 5 | H | FS#2
4 | W-B03 | Entra ID SSO primitive | 5 | H | FS#2
5 | W-B13 | Outbound email gateway | 5 | H | FS#2
Track totals (indicative): ~51–82 MD across 21 rows.
Block 5 — Sprint Plan (Core BE)
Sprint | Core BE goal | Exit criterion
S1 (W1–W2) | Monorepo + module template + SSO + magic link + permissions + audit + RLS + outbox + pg-boss + email gateway + observability + commons | D-B01..D-B08 + D-B10 + D-B11 green; Planner team unblocked for Action domain work
S2 (W3–W4) | Rate limiter + kill switches + MS Graph adapter hardening (retry / backoff / subscription renewal) | D-B07 + D-B09 green; Planner transcript webhook + MS Planner sync teams unblocked
S3 (W5–W6) | Performance tuning on hot endpoints; index review; retention/archival path design | No performance regressions; SLO dashboards green
S4 (W7–W8) | Data retention + admin deletion + export-on-request hook; pre-pilot hardening | Retention + deletion round-trip through audit log
Block 6 — Track-specific Risks
ID | Risk | P | I | Mitigation | Owner | Status
RB-01 | Graph application permission approval delayed (D-02) | M | H | Fallback to magic-link auth for development; parallel-track directory sync until consent lands | IT + PM | Open
RB-02 | RLS + pool-client-per-request adds latency to hot endpoints | L | M | Benchmark in S1; connection-pool sizing per load test in S4 | FS#2 + SRE | Open
RB-03 | Outbox relay backlog grows under event spikes | M | M | Add parallelism with per-aggregate ordering; alerting on lag | FS#2 | Open
RB-04 | Permissions engine logic missed an edge case; cross-hierarchy leak | L | H | Exhaustive unit test matrix; integration test with pilot-shaped org tree; included in W-QA03 adversarial test scope | FS#2 + QA | Open
RB-05 | Email deliverability (SES reputation) low on first pilot send | L | M | Warm up SES domain pre-pilot; monitor bounce/complaint rate; unsubscribe honoured | FS#2 + IT | Open
Block 7 — Definition of Done (track-level)
• All D-B01 .. D-B11 deliverables accepted.
• Coverage ≥ 70% on all Core BE packages.
• SLO dashboards (CloudWatch + Langfuse) green for 2 hours on staging.
• Permission matrix exhaustively tested.
• SAST + dependency audit clean.
• Architecture documented in 02-Contract Block 1 fields + inline in code.
• Core BE patterns demonstrably reusable (Planner track uses them end-to-end without modification).
Block 8 — Open Questions
Question | Owner | Needed by
Self-hosted Langfuse vs managed cloud (D-05) | CTO | W1
Redis presence for rate limiter or Postgres-only | FS#2 + CTO | W1
SES sending-domain name (reuses existing SETA domain?) | IT | W2
Retention windows per entity type (action · transcript · evidence · audit log) — default is indefinite; any exceptions? | Sponsor + Legal | W4
Tracing sampling rate on pilot-staging env | FS#2 + SRE | W2
MS Graph subscription resource scopes — are chat / transcript scopes granted at tenant level or filtered by Admin? | IT + Admin | W2

## Track-CoreFrontend
Sheet: Track-CoreFrontend
Horizontal track. Next.js multi-zone setup, design system tokens, @future/ui, @future/app-layout, theme toggle, notifications popover, shared tRPC client, SSE client, zone scaffolding generator, shared FE commons. No Planner-specific UI lives here.
Block 1 — Purpose
Deliver the foundational frontend slice that every Future zone will reuse. Multi-zone architecture, design system aligned to DESIGN.md, common components, layout primitives — enough to unblock Planner's UI work and to provide a scaffolding pattern for the remaining 10 module zones.
Block 2 — Scope
2.1 In scope
03-Scope Block 1 WBS rows W-F01 .. W-F19:
• Multi-zone Next.js setup (11 zones + shell; routing conventions; zone proxy).
• Design system tokens + Tailwind v4 + CSS variables + dark (default) + light.
• @future/ui component library (Button · Input · Textarea · Alert · Skeleton · Spinner · Dialog · Drawer · Card · Table · DataTable · Dropdown · Select · Tabs · Tooltip · Badge).
• @future/app-layout (AppLayout · SidebarProvider · SidebarRenderer · NavbarRenderer · NavGroup static/dynamic · PermissionProvider).
• Auth (FE) — session hydration from httpOnly cookie · session context · redirect-to-shell on 401 · token-aware tRPC client.
• Permission-aware rendering (useCanAccess hook · PermissionContext · permission-filtered NavGroups).
• Theme toggle + next-themes + cookie persistence.
• Real in-app notifications popover (no stub).
• Shared tRPC client + React Query wrapper.
• SSE streaming client primitive.
• Zone scaffolding generator.
• Responsive + mobile layouts (sidebar collapse · viewport-aware dialogs/drawers).
• Storybook + visual regression + axe a11y audit.
• Shared FE commons (date / time / currency formatters · permissions hook · toast · form helpers).
2.2 Out of scope
• Planner-specific UI (views, HITL queue, admin console, conversational UI) — lives in the Planner track.
• Any module-specific page or widget — those belong to their module tracks.
• Backend logic — Core Backend track owns.
• AI-specific runtime — Core AI Agent track owns.
• Internationalisation (i18n) — English only per constraint.
2.3 Dependencies
• Core Backend delivers kernel.getMyPermissions tRPC endpoint by end of W1 so PermissionProvider can hydrate.
• Core Backend delivers session cookie + SSO redirect pattern by end of W1.
• Designer-Lead provides finalised tokens for any components not already locked in DESIGN.md.
Block 3 — Deliverables & Acceptance
# | Deliverable | Acceptance | Evidence | Milestone
D-F01 | Multi-zone scaffold | Every zone boots independently; cross-zone hard-link lint rule enforced; shell owns SSO + magic-link | Zone sign-in + navigation proof | M01
D-F02 | Design tokens + Tailwind | Tokens drive every component; lint flags hardcoded colors; theme tokens validated | Storybook snapshot | M01
D-F03 | @future/ui core set | 16 components documented in Storybook; a11y audit clean; variants match design | Storybook deploy | M01
D-F04 | @future/app-layout | Zones mount AppLayout with own nav config; static vs dynamic NavGroup enforced (no dual-shape) | Storybook + zone integration | M01
D-F05 | Session + Permission + Theme wiring | Unauth redirects to shell; permission-filtered nav; theme toggle persists | Integration test across 2 zones | M01 / M02
D-F06 | Notifications popover | Real live events render; unread count; mark-as-read via SSE | Integration test | M02
D-F07 | Shared tRPC + SSE + FE commons | Typed end-to-end; optimistic mutation helpers documented | Unit tests | M01
D-F08 | Zone scaffolding generator | turbo gen workspace creates a runnable zone matching the pattern | Manual generation proof | M01
D-F09 | Responsive + mobile | Mobile / tablet visual QA across zones; touch targets ≥ 44px | Visual regression suite | M03
D-F10 | Storybook + visual regression | Storybook at internal URL; visual regression baseline green | CI status | M02
Block 4 — WBS (task-level)
Full WBS on 03-Scope Block 1 rows W-F01 .. W-F19. Top 5 by effort:
Rank | ID | Feature | Effort High (MD) | Confidence | Owner
1 | W-F03 | @future/ui core set | 8 | H | FS#1
2 | W-F04 | @future/app-layout | 7 | H | FS#1
3 | W-F01 | Next.js multi-zone setup | 5 | H | FS#1
4 | W-F09 | React Query / tRPC client | 5 | H | FS#1
5 | W-F12 | Responsive + mobile layouts | 5 | M | FS#1
Track totals (indicative): ~47–81 MD across 19 rows.
Block 5 — Sprint Plan (Core FE)
Sprint | Core FE goal | Exit criterion
S1 (W1–W2) | Multi-zone + tokens + @future/ui core + @future/app-layout + session + permission + shared tRPC + commons + zone scaffolding | D-F01..D-F05, D-F07, D-F08 green; Planner team unblocked for views
S2 (W3–W4) | Theme toggle + notifications popover + SSE primitive + Storybook + visual regression | D-F06 + D-F10 green
S3 (W5–W6) | Responsive + mobile layouts · a11y audit sweep across zones | D-F09 green; axe audit clean
S4 (W7–W8) | Polish · lint rules (hardcoded colors, design-token adherence) · performance sweep | Lint blocks non-token colors; FE Lighthouse passes
Block 6 — Track-specific Risks
ID | Risk | P | I | Mitigation | Owner | Status
RF-01 | Design-token lint doesn't catch all hardcoded colors | L | M | Combine ESLint + Stylelint rule + Storybook check; review in code review | FS#1 + Designer | Open
RF-02 | Notifications popover behind SSE has reconnect / backpressure edge cases | M | M | Unit test reconnect + cancel; staging soak test pre-M04 | FS#1 | Open
RF-03 | Permission-filtered nav lags after permission change (cache staleness) | M | M | Cache invalidation on permission-change event; fallback to re-fetch on route change | FS#1 | Open
RF-04 | Responsive breakpoints chosen without designer pass | M | M | Designer-Lead reviews responsive breakpoints in S3 | Designer + FS#1 | Open
RF-05 | Storybook deploy URL not reachable for Designer | L | L | Internal S3 static bucket; Designer gets access by Kickoff | FS#1 + DevOps | Open
Block 7 — Definition of Done (track-level)
• All D-F01 .. D-F10 deliverables accepted.
• Coverage ≥ 70% on @future/ui and @future/app-layout.
• Axe a11y audit clean on Storybook and on representative zone pages.
• Visual regression suite green.
• Cross-zone <a> lint rule blocks <Link> between zones.
• DESIGN.md fully implemented; no deviations without designer sign-off.
• At least two zones (Planner + admin) consume the foundations without modification.
Block 8 — Open Questions
Question | Owner | Needed by
Storybook deployment target (internal S3 · GitHub Pages · other) | FS#1 + DevOps | W1
Does Planner admin console get a separate zone (web-admin) or live inside web-planner? | PM + FS#1 | W2
Theme toggle placement (global header vs user menu) | Designer + FS#1 | W2
Notifications popover transport — SSE vs polling fallback for environments that block SSE? | FS#1 + SRE | W3
Virtualisation for large lists (Grid view) — shared primitive or per-zone? | FS#1 | W3
Do we need a <DataTable> with server-side pagination primitive, or per-zone custom? | FS#1 | W2

## Track-CoreAIAgent
Sheet: Track-CoreAIAgent
Horizontal track. Foundational AI plumbing: LLM client, prompt store, confidence scoring, HITL routing engine, tool/MCP registry, ToolGateway pipeline, sub-agent runner, SSE contract, Langfuse telemetry. Phase 2 adds prompt-injection defence, permission enforcement at the AI boundary, free-form query router, cost metering, adversarial eval CI. Planner-specific sub-agents, extraction prompts, conversational executor, and webhook handlers live on the Planner track (W-P10..W-P18, W-P25..W-P27).
Block 1 — Purpose
Deliver the foundational AI slice that every Future module will reuse. Phase 1 (W1–W4) locks the primitives; Phase 2 (W5–W8) hardens security and unlocks free-form queries beyond the bounded Phase 1 tool registry.
Block 2 — Scope
2.1 In scope
03-Scope Block 1 WBS rows W-A01 .. W-A14, split into two phases.
Phase 1 — W1–W4 (foundational):
• LLM client (Vercel AI SDK + OpenAI · model selector · retry · cost accounting).
• Prompt store (versioned templates · env override · fixtures).
• Confidence scoring framework (H/M/L derivation rules · drift harness).
• HITL routing engine (routing matrix · fallback · review window · auto-expiry · backlog alert).
• Tool + MCP registry (bounded, introspection via tRPC meta).
• ToolGateway 10-step pipeline (auth · permission · taint · rate · budget · args-validate · execute · sanitize · log · trace).
• Sub-agent runner pattern (tool-calling loop · max-steps ceiling · SSE events).
• Langfuse telemetry + OTel wiring.
• SSE contract (stream event types · backpressure · cancel).
Phase 2 — W5–W8 (fine-tuning · security · free-form queries):
• Prompt-injection defence (tenant-authored-text redaction · delimiter strategy · regression suite).
• Permission enforcement at the AI boundary (result-fetch check · structured-query audit · composition-derived disclosure guard).
• Free-form query router (multi-sub-agent fan-out · synthesizer · disambiguation · query-preview contract).
• Cost metering + budget + circuit breaker + admin dashboard.
• Prompt tuning + eval CI.
2.2 Out of scope
• Planner-specific sub-agent for transcript extraction — lives on Planner track as W-P12, consumes this track's runner.
• Planner-specific extraction prompts — lives on Planner track; tuned by AI Eng alongside Planner.
• Transcript webhook handler — Core BE track (W-B14 MS Graph scaffolding) + Planner track (W-P11).
• Conversational AI UI — Planner track (W-P25) and Core FE (SSE client).
• Conversational query executor for Planner domain — Planner track (W-P26), using this track's tool registry + ToolGateway.
• Write-capable agents (Phase 2 drafts + approvals are outside this MVP). Read-only in pilot.
• Module-specific sub-agents for People, Time, Projects, Finance, etc. (deferred to subsequent module tracks).
2.3 Dependencies
• OpenAI API key + budget guardrails (D-04).
• Langfuse deployment target confirmed (D-05).
• Core BE: audit log (for tool-call provenance) · pg-boss (for async agent jobs in Phase 2) · permissions engine (for canDo calls inside ToolGateway).
• Core FE: SSE client primitive (for streaming sub-agent output).
Block 3 — Deliverables & Acceptance
Phase 1 deliverables (must land by M02 / W4)
# | Deliverable | Acceptance | Evidence | Milestone
D-A01 | LLM client + model selector | Prompt round-trip; cost per call captured in Langfuse; provider swap is one-file change | Langfuse trace + unit test | M01
D-A02 | Prompt store | Template change is a migration; every LLM call references a prompt version in its trace | Migration test + trace proof | M01
D-A03 | Confidence scoring framework | Confidence band on every proposal; baseline eval vs BA ground-truth passes | Eval suite run | M02
D-A04 | HITL routing engine | Routing tested against full role matrix; expiry + backlog hooks call deterministic paths | Integration tests | M02
D-A05 | Tool + MCP registry + ToolGateway | Unauthorised tool call denied with audit; taint flows end-to-end; sanitisation drops disallowed fields | Integration tests | M02
D-A06 | Sub-agent runner pattern | Base runner executes a canned agent; loop terminates at max-steps; SSE contract stable | Integration + runner demo | M02
D-A07 | Langfuse telemetry | Every LLM + tool call appears; trace navigable end-to-end | Langfuse dashboard proof | M01
D-A08 | SSE contract | Stream events parse round-trip; cancel aborts upstream; backpressure handled | Contract tests | M02
Phase 2 deliverables (must land by M05 / W8)
# | Deliverable | Acceptance | Evidence | Milestone
D-A09 | Prompt-injection defence | Adversarial prompts trigger refusal; regression suite gates CI | Red-team suite + CI status | M05
D-A10 | Permission enforcement at AI boundary | Penetration test returns zero permission-leak incidents (tied to R-07 / RP-04) | PM + BA test report | M05
D-A11 | Free-form query router | Baseline 30-query eval ≥ 80% first-attempt correctness; disambiguation surfaces when router confidence low | Eval suite green | M05
D-A12 | Cost metering + budget + circuit breaker | Per-tenant daily budget blocks excess calls; breaker short-circuits on breach; dashboard live | Breaker test + dashboard proof | M05
D-A13 | Prompt tuning + eval CI | Eval runs on every prompt change; regression blocks merge | CI gate status | M05
Block 4 — WBS (task-level)
Full WBS on 03-Scope Block 1 rows W-A01 .. W-A14. Top 5 by effort:
Rank | ID | Feature | Effort High (MD) | Confidence | Owner
1 | W-A12 | Free-form query router (Phase 2) | 9 | L | AI Eng
2 | W-A06 | ToolGateway pipeline (Phase 1) | 8 | M | AI Eng
3 | W-A04 | HITL routing engine (Phase 1) | 7 | M | AI Eng
4 | W-A11 | Permission enforcement at AI boundary (Phase 2) | 7 | L | AI Eng
5 | W-A03 | Confidence scoring framework (Phase 1) | 6 | L | AI Eng
Track totals (indicative): ~48–80 MD across 14 rows.
Block 5 — Sprint Plan (Core AI)
Each phase has its own exit criterion.
Sprint | Phase | Core AI goal | Exit criterion
S1 (W1–W2) | Phase 1 | Install AI stack; ship LLM client + prompt store + tool registry + Langfuse + SSE contract skeleton | Prompt round-trips; Langfuse trace present; tool registry enumerates; runner scaffolding compiles
S2 (W3–W4) | Phase 1 | Complete ToolGateway pipeline + HITL routing engine + confidence scoring + sub-agent runner end-to-end | Phase 1 exit: D-A01..D-A08 green; Planner team can consume runner + registry to build the transcript sub-agent (Planner W-P12)
S3 (W5–W6) | Phase 2 | Prompt-injection defence + permission enforcement at AI boundary + router skeleton | Red-team regression suite passes; permission-enforcement unit tests pass; router wiring in place
S4 (W7–W8) | Phase 2 | Free-form router + synthesizer + cost metering + eval CI + pre-pilot adversarial test | Phase 2 exit: D-A09..D-A13 green; penetration test with PM + BA returns zero permission-leak incidents (M05)
Block 6 — Track-specific Risks
ID | Risk | P | I | Mitigation | Owner | Status
RA-01 | Confidence scoring rules under-specified; calibration drifts across prompt versions | M | M | Drift harness runs on every prompt change; baseline eval held as regression gate; AI Eng documents derivation rules in prompt-store versioning | AI Eng | Open
RA-02 | Phase 2 router fan-out unbounded → OpenAI cost runaway (also R-11 on 08-Risks-Issues) | M | M | Hard cap on concurrent sub-agent spawn; circuit breaker on per-tenant daily budget (W-A13); Admin budget dashboard | AI Eng | Open
RA-03 | Permission-enforcement at AI boundary misses a composition-derived disclosure path | M | H | Composition-sensitivity test in S3; penetration test in S4; tool-authoring checklist for every tool added | AI Eng + QA | Open
RA-04 | Single AI Engineer as bus-factor point of failure (also R-06) | M | M | Pairing with FS#2 on Phase 1 primitives; design decisions captured on 02-Contract Block 1 + in prompt-store DB versioning; critical logic reviewed by Tech Lead | AI Eng + PM | Open
RA-05 | Langfuse self-hosted ECS deployment slip (if that path is chosen) | L | M | Managed-cloud Langfuse as fallback; decision (D-05) closed by end W1 | CTO | Open
RA-06 | Phase 2 eval baseline not representative of pilot usage | M | M | Baseline built from pilot-shaped queries with BA input in S4; update after pilot W2 | AI Eng + BA | Open
Block 7 — Definition of Done (track-level)
• All D-A01 .. D-A13 deliverables accepted.
• Coverage ≥ 70% on Core AI packages.
• Penetration-style test on AI boundary returns zero permission-leak incidents.
• Red-team adversarial prompt suite green.
• 30-query baseline eval ≥ 80% first-attempt correctness.
• Budget circuit breaker demonstrably short-circuits at per-tenant cap.
• Langfuse traces navigable end-to-end for a representative query (router → sub-agent → synthesiser → tool calls → result).
• Phase 1 primitives reused by Planner transcript sub-agent (Planner W-P12) without core changes.
Block 8 — Open Questions
Question | Owner | Needed by
OpenAI API key provisioning path (org-level vs project-level) (D-04) | PM + IT | W1
Langfuse: self-hosted ECS vs managed cloud (D-05) | CTO | W1
Prompt-store schema — DB column type for long templates (text vs jsonb) | AI Eng + FS#2 | W1
Confidence-scoring initial thresholds — fixed values vs tuned during pilot? | AI Eng + BA | W3
Phase 2 router: start with "pre-built queries only" fallback if router ≤ 80% in eval? | AI Eng + PM | W6
Per-tenant daily budget default value for W-A13 | Admin + PM | W5
Cost-meter granularity (per-call vs per-session) | AI Eng | W4
Write path (drafts + approvals) — confirm explicitly out of scope for this MVP? | PM + Sponsor | W1